AJACE INC.  ·  ECHOMIND ENTERPRISE  ·  ISO 9001:2015 EVIDENCE

# Requirement Change Record — EchoMind (Project 2)

# Document control

| Field | Value |
| --- | --- |
| Document ID | EM26-30 |
| Title | Requirement Change Record — EchoMind (Project 2) |
| Version | 1.1 |
| Issue date | 2026-10-14 |
| Status | Rev 1.1 issued for approval; rev 1.0 approved 2026-10-14 (AR-2026-006) |
| Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA |
| Project | EchoMind Product (Project 2) |
| Procedure | SOP-04 §6; SOP-06; form FRM-02 |
| Registers | EM26-20 (functional), EM26-21 (non-functional) |
| Prepared by | Richard Watson Stephen Amudha (Lead Engineer) — 2026-10-14 |
| Reviewed by | Alexander Peter (EchoMind Project Lead) — rev 1.1 to confirm |
| Quality assurance | Sheryl Nazareth (QA / MR) — rev 1.1 to confirm |
| Approved by | Anita Johan (Managing Director) — rev 1.1 to confirm |

# 1. Purpose

Every change to the agreed requirements — what changed, why, who asked, the meeting where it was decided and where that meeting is recorded, the impact, how it was implemented and how it was verified.

# 2. Change log

| Change | Date | Requirements | Change | Reason | Requested by | Meeting recorded in | Impact | Decision | Implemented (commit — version) | Verified | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RC-2025-01 | 2025-08-05 | FR-2025-01 … 05 | Requirements fixed in the signed SOW: offline on-premises system, BYOA pilot | Contract | 2025 university pilot customer | EM26-28 CON-2025-01; review record DR-2025-09 | Baseline for the 2025 appliance | Accepted | Delivered Sep 2025 | Acceptance test on delivery | Closed |
| RC-2026-01 | 2026-01 | FR-PL-01; NFR-D01 | Platform changed from a single RTX 4090 PC to the DGX Spark | Capacity and portability | EchoMind team | EM26-19 review log › CR-2026-01; review record CR-2026-01 | All services ported; new platform | Accepted | 4b90b36, c751d79 — v1.0.0 | TC-EM-OPS-105 | Closed |
| RC-2026-02 | 2026-03 | FR-VC-01; NFR-P04, NFR-P07 | Conversation engine: Kyutai Unmute → NVIDIA PersonaPlex | Client feedback: not natural, too slow | Client A; Client B (Bahrain) | EM26-19 review log › CR-2026-03; review record CR-2026-03 | Voice engine replaced | Accepted | Trial (compared in the QASC 2026 paper) | Client review CR-2026-04 | Superseded by RC-2026-03 |
| RC-2026-03 | 2026-04 | FR-VC-01, FR-VC-02; NFR-P04 | Conversation engine: PersonaPlex → own dual-loop flow grounded in the client's knowledge base | Client feedback: must use the client's large data | Client A; Client B (Bahrain) | EM26-19 review log › CR-2026-04; review record CR-2026-04 | New voice architecture; Nemotron speech recognition | Accepted | ddc0aa3, d89aeda — v1.1.0 | Research harness E4/E7: 636 ms median | Closed |
| RC-2026-04 | 2026-03 → 07 | FR-KC-04; NFR-Q01 … Q05 | DoD FMR retrieval: BookRAG and PageIndex tried; hierarchical section → chunk retrieval kept | 7,300-page regulation; performance | Client A; Client B (Bahrain) | EM26-19 review log › CR-2026-02; review record CR-2026-02 | Retrieval design; BookRAG switched off | Accepted | 18715c7 — v1.1.0; 2decb99 — v1.3.0 | Golden suite 50/52 (BookRAG 43/52) | Closed |
| RC-2026-05 | 2026-04 | FR-LT-01, FR-LT-02; NFR-P01, NFR-P06 | Live transcript: better speech model with fallback; chat from Ollama to TensorRT-LLM | Client feedback: accuracy and speed | Client A | EM26-19 review log › CR-2026-06; review record CR-2026-06 | Speech recognition and LLM serving changed | Accepted | d89aeda — v1.1.0; b6a70d8 — v1.2.0; 80375c6 — v1.3.0 | Voice end-to-end test; acceptance run 4 | Closed |
| RC-2026-06 | 2026-05 | FR-SA-01 … 03 | New requirement: listen-only Silent Assistant that puts data on screen and never replies | Client request after the demonstration | Client C (law firm) | EM26-19 review log › CR-2026-07; review record CR-2026-07 | New module beside live transcription | Accepted | ec9b180 — v1.2.0; 7f2658a — v1.3.0 | Scenario harness | Closed |
| RC-2026-07 | 2026-06 | FR-DS-01 … 04 | New requirement: Document Studio — PPT and PDF locally, with and without a template | Client requirement (mediator contract) | Client D (Gulf region) | EM26-19 review log › CR-2026-09; review record CR-2026-09 | New module; on-device image model | Accepted | 2d23f40, 66356f9 — v1.2.0 | TC-EM-DGEN-110 (run 4) | Closed |

# 3. Requirements added from internal reviews

| Date | Requirement | Raised by | Meeting recorded in | Implemented | Verified |
| --- | --- | --- | --- | --- | --- |
| 2026-04 | FR-PL-06 — reach a deployed unit with no network (boot-time hotspot and landing page) | Alexander Peter (Project Lead) | EM26-19 review log › CR-2026-05; review record CR-2026-05 | Deployment unit; configuration to version control (AC-26) | Demonstrated on the unit |
| 2026-05 | FR-BR-01, FR-BR-02 — group discussions with speaker separation and a meeting report | EchoMind team | EM26-19 review log › CR-2026-08; review record CR-2026-08 | f540976, cf463aa, e1a337b — v1.2.0 | TC-EM-BRD-111 (run 4) |

# 4. Requested, not yet accepted

| Date | Request | Client | Recorded in | Status |
| --- | --- | --- | --- | --- |
| 2026-08 | EchoMind IoT — agritech sensors; vehicle inspection | Client E (Asia-Pacific) | EM26-28 CON-2026-04 | Requirements and contract in evaluation |

# 5. How a change is handled

- Raised in a client or design meeting; the meeting is recorded as a review in EM26-19 with the decision and actions.

- Impact on scope, design and schedule assessed; significant changes use FRM-02 and the change register REG-07 (SOP-06 §6).

- Requirement registers EM26-20 / EM26-21 updated; delivered in the next version; verified by its test.