## Test executions
Test executions
EM26-34 Test Execution Register — every recorded test execution, Sep 2025 → Oct 2026 (38 runs). Issued 2026-10-14.
Date | Version | Level | Test | Executed by | Result | Defect / NC | Evidence
2025-09 | 2025 appliance | Acceptance | End-to-end test: transcription and contextual Q&A on the delivered unit | AJACE team | Pass — accepted | — | Project documentation (controlled copy)
2025-09-05 | 2025 appliance | Regression | Regression after QA-FAIL-01 (REG-2025-01) | AJACE QA | Pass — defect resolved | DEF-2025-01 | 2025 records (controlled copy)
2026-07-29 12:39 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 29/52 | — | eval/reports/eval_20260729-123923.json
2026-07-29 12:48 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 27/52 | — | eval/reports/eval_20260729-124803.json
2026-07-29 13:00 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 44/52 | — | eval/reports/eval_20260729-130027.json
2026-07-29 13:09 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 47/52 | — | eval/reports/eval_20260729-130900.json
2026-07-29 13:18 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-131815.json
2026-07-29 13:45 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-134521.json
2026-07-29 18:45 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-184535.json
2026-07-29 18:54 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 47/52 | — | eval/reports/eval_20260729-185435.json
2026-07-29 19:51 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 43/52 | — | eval/reports/eval_20260729-195109.json
2026-07-29 19:59 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 0/7 — smoke subset | — | eval/reports/eval_20260729-195914.json
2026-07-29 20:03 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 0/7 — smoke subset | — | eval/reports/eval_20260729-200328.json
2026-07-29 20:10 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-201050.json
2026-07-29 20:33 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-203340.json
2026-07-29 20:42 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 49/52 | — | eval/reports/eval_20260729-204248.json
2026-07-29 21:52 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-215246.json
2026-07-29 22:47 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 46/52 | — | eval/reports/eval_20260729-224713.json
2026-07-29 22:56 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-225633.json
2026-07-29 22:56 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-225644.json
2026-07-29 23:10 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 48/52 | — | eval/reports/eval_20260729-231034.json
2026-07-30 01:59 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 43/52 | — | eval/reports/eval_20260730-015940.json
2026-07-30 02:06 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 50/52 | — | eval/reports/eval_20260730-020659.json
2026-08-06 14:22 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 42/52 | isolation regression found → NC-2026-001 | eval/reports/eval_20260806-142233.json
2026-08-06 14:32 | v1.3.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 49/52 | — | eval/reports/eval_20260806-143249.json
2026-08-07 | v1.3.0 | Research harness | E1–E10: latency, citations, grounding, isolation, injection, barge-in | Richard Watson Stephen Amudha | Results frozen (NFR-P01…S03) | NC-2026-007 (claims) | eval/paper/results
2026-09-21 | v1.4.0 | Voice end-to-end | 12 spoken turns on two personas; barge-in; GPU fault check | Richard Watson Stephen Amudha | Pass — 22 review findings fixed | — | commit ff29843
2026-09-22 | v1.4.0 | Restore test | Backup restored into a throwaway volume | Richard Watson Stephen Amudha | Pass — integrity_check ok, 32 tables | — | backup_checksum_20260922.sha256
2026-09-22 13:53 | v1.4.0 | Golden suite | Golden questions (banking, conversation, DoD FMR, health, law, meetings, retail) | Richard Watson Stephen Amudha | 9/52 | corpus absent → NC-2026-008 | eval/reports/eval_20260922-135322.json
2026-09-28 | v1.4.0 | Unit tests | Backend and voice suites; front-end type check | Richard Watson Stephen Amudha | Fail — 5 tests, 20 type errors | NC-2026-010 | commits 5ddf8a6, 736ea61
2026-10-06 | v1.4.0 code | Acceptance | 13 acceptance test cases — run 1 | Richard Watson Stephen Amudha | 7 pass, 4 fail, 1 not executed, 1 blocked | NC-2026-012 … 015 | 15_Testing/Execution_Records/run1
2026-10-06 | fixes e0ed4d0 | Acceptance | Run 2 — re-test of the four fixes | Richard Watson Stephen Amudha | Fixes pass; logout logged as anonymous | QA-FAIL-2026-06 | Execution_Records/run2
2026-10-06 | v1.4.1 | Acceptance | Run 3 after deployment | Richard Watson Stephen Amudha | Embedding service down while healthy | NC-2026-016 | Execution_Records/run3
2026-10-06 | v1.4.1 | Acceptance | Run 4 — full re-test | Richard Watson Stephen Amudha | 11/11 executable pass | — | Execution_Records/run4
2026-10-06 | v1.4.1 | Unit tests | Backend 50, voice 131, type check | Richard Watson Stephen Amudha | Pass | — | Release record v1.4.1 §3
2026-10-07 | v1.4.1 | CI | Unit tests and type check on every push (run 37561379960) | GitHub Actions | Pass | — | GitHub Actions
2026-10-07 | v1.4.1 | CI | Deliberately broken test to prove CI fails (run 37561804619) | GitHub Actions | Fail as intended | NC-2026-010 closed | GitHub Actions
2026-10-07 | v1.4.1 | External check | Public site requires login — every 6 hours (run 37561803121) | GitHub Actions | Pass (401) | — | GitHub Actions

## By version
By version
Live formulas
Version | Window | Test runs | Of which failed or blocked
v1.0.0 | Jan–Feb 2026
v1.1.0 | Mar–Apr 2026
v1.2.0 | May–Jun 2026
v1.3.0 | Jul–Aug 2026
v1.4.0 | Sep 2026
v1.4.1 | Oct 2026

## Document control
Document control
Document control
Field | Entry
Document ID | EM26-34
Title | Test Execution Register
Version | 1.0
Issue date | 2026-10-14
Status | Issued for approval
Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA
Project | EchoMind Product (Project 2)
Prepared by | Richard Watson Stephen Amudha (Lead Engineer) — 2026-10-14
Reviewed by | Alexander Peter (EchoMind Project Lead) — to confirm
Quality assurance | Sheryl Nazareth (QA / MR) — to confirm
Approved by | Anita Johan (Managing Director) — to confirm