## Actual timeline
Date | Milestone | Reference | Status
2026-01 | Decision to move from the 2025 PC appliance to a portable AI supercomputer (DGX Spark) | EM26-18 CR-2026-01 | Done
2026-02-05 | First DGX Spark; 2025 code ported — first commit | 4b90b36, c751d79 | Done
2026-03 | Client requirements: personal assistant, conversation assistance, DoD FMR knowledge base | EM26-18 CR-2026-02; 95d3512 | Done
2026-03-20 | TensorRT-LLM integrated beside Ollama | 06e788a | Done
2026-04-08 | Own dual-loop conversation architecture; Nemotron speech recognition | ddc0aa3, d89aeda | Done
2026-04 | Field-deployment hotspot (Project Lead design review) | EM26-18 CR-2026-05 | Done
2026-05 | Silent Assistant (law-firm request) and Boardroom | ec9b180, f540976, e1a337b | Done
2026-06-20 | Document Studio (Gulf client request) | 2d23f40, 66356f9 | Done
2026-06-27 | Phase 0b auth + vertical packs (single-day batch) | c9bad3d…b9f076e | Done
2026-07-29 | TRT-LLM platform, evaluation harness, security enablement | 80375c6, 12f7219, 9810e98 | Done
2026-08-16 | RAG overhaul, Silent Assistant v2 | 7e582e1, 7f2658a | Done
2026-09-21 | Voice redesign | ff29843 | Done
2026-09-22 | Release v1.4.0 + QMS documentation | eaa7b1a, 9efb134 | Done
2026-10-06 | Deployment of v1.4.0 code; login restored | REG-08 | Done
2026-10-06 | Release v1.4.1 — defect corrections | f1b8445 | Done
2026-10-07 | ISO pre-audit / dry run | — | Scheduled
2026-10-14 | ISO 9001 surveillance audit | — | Scheduled

## Commits by month
Month | Commits
2026-02 | 84
2026-03 | 20
2026-04 | 12
2026-05 | 3
2026-06 | 41
2026-07 | 19
2026-08 | 20
2026-09 | 12
2026-10 | 19

## Open actions
Action | Source | Target date | Owner
Install off-host backup timer | D14 / REG-03 R-02 | 2026-10-13 | Kishan Haravu Pradeep
Restore evaluation corpus | NC-2026-008 | 2026-10-13 | Richard Watson Stephen Amudha
Agree NFR targets | REG-09 A-1 | Done 2026-10-07 | Anita Johan
CI for unit suites + API tests | NC-2026-010 / LL-2026-12 | Unit suites done 2026-10-07; API tests open | Richard Watson Stephen Amudha
Fix NC-2026-012…015 | EM26-15 | Done 2026-10-06 | Richard Watson Stephen Amudha
Deploy only from built images | NC-2026-011 | From v1.4.1 (2026-10-06) | Richard Watson Stephen Amudha
Verify model licences | C1–C3 / R-10 | 2026-10-31 | Richard Watson Stephen Amudha
Retention policy | B3/D10 / R-06 | 2026-10-31 | Kishan Haravu Pradeep
Hotspot configuration under version control | EM26-18 AC-26 | 2026-10-31 | Alexander Peter