AJACE INC.  ·  ECHOMIND ENTERPRISE  ·  ISO 9001:2015 EVIDENCE

# Scheduling Review – EchoMind Enterprise (Feb–Oct 2026)

# Document control

| Field | Value |
| --- | --- |
| Document ID | EM26-12 |
| Title | Scheduling Review – EchoMind Enterprise (Feb–Oct 2026) |
| Version | 1.0 |
| Date | 2026-10-06 |
| Status | APPROVED — 2026-10-07 (AR-2026-001) |
| Product / area | EchoMind Enterprise (repository RW2523/echomind-enterprise) |
| Prepared by | Richard Watson Stephen Amudha (Lead Engineer) |
| Reviewed by | Alexander Peter (EchoMind Project Lead) |
| Quality assurance | Sheryl Nazareth (QA / MR) |
| Approved by | Anita Johan (Managing Director) — 2026-10-07 |

# Purpose

Record the actual delivery timeline of the rebuilt product, its milestones and schedule risks.

This record was prepared on 2026-10-06 from the git history and the QMS registers. Dates in it are the dates of the underlying commits and records, not the date of this document. Review and approval reviewed by Alexander Peter (EchoMind Project Lead) and approved by Anita Johan (Managing Director) on 2026-10-07 — approval record AR-2026-001.

# Activity by month (commits on main)

| Month | Commits |
| --- | --- |
| 2026-02 | 84 |
| 2026-03 | 20 |
| 2026-04 | 12 |
| 2026-05 | 3 |
| 2026-06 | 41 |
| 2026-07 | 19 |
| 2026-08 | 20 |
| 2026-09 | 12 |
| 2026-10 | 19 |

# Milestones

| Date | Milestone | Reference | Status |
| --- | --- | --- | --- |
| 2026-01 | Decision to move from the 2025 PC appliance to a portable AI supercomputer (DGX Spark) | EM26-18 CR-2026-01 | Done |
| 2026-02-05 | First DGX Spark; 2025 code ported — first commit | 4b90b36, c751d79 | Done |
| 2026-03 | Client requirements: personal assistant, conversation assistance, DoD FMR knowledge base | EM26-18 CR-2026-02; 95d3512 | Done |
| 2026-03-20 | TensorRT-LLM integrated beside Ollama | 06e788a | Done |
| 2026-04-08 | Own dual-loop conversation architecture; Nemotron speech recognition | ddc0aa3, d89aeda | Done |
| 2026-04 | Field-deployment hotspot (Project Lead design review) | EM26-18 CR-2026-05 | Done |
| 2026-05 | Silent Assistant (law-firm request) and Boardroom | ec9b180, f540976, e1a337b | Done |
| 2026-06-20 | Document Studio (Gulf client request) | 2d23f40, 66356f9 | Done |
| 2026-06-27 | Phase 0b auth + vertical packs (single-day batch) | c9bad3d…b9f076e | Done |
| 2026-07-29 | TRT-LLM platform, evaluation harness, security enablement | 80375c6, 12f7219, 9810e98 | Done |
| 2026-08-16 | RAG overhaul, Silent Assistant v2 | 7e582e1, 7f2658a | Done |
| 2026-09-21 | Voice redesign | ff29843 | Done |
| 2026-09-22 | Release v1.4.0 + QMS documentation | eaa7b1a, 9efb134 | Done |
| 2026-10-06 | Deployment of v1.4.0 code; login restored | REG-08 | Done |
| 2026-10-06 | Release v1.4.1 — defect corrections | f1b8445 | Done |
| 2026-10-07 | ISO pre-audit / dry run | — | Scheduled |
| 2026-10-14 | ISO 9001 surveillance audit | — | Scheduled |

# Schedule risks and actions

- Risk: single developer — work arrives in bursts (84 commits in Feb, 3 in May) — Action: REG-03 R-03; plan capacity at management review.

- Risk: upstream dependency outage (NeMo @main, NC-2026-006) — Action: pinned 2026-09-22.

- Risk: shared GPU with another project slows or blocks restarts — Action: GPU sharing policy (lesson LL-2026-05).

- Risk: open pre-audit actions — Action: tracked with owners and dates on the project board (65 tickets).

# Forward plan

No forward delivery dates have been approved for the product. The SDLC record (EM26-12_SDLC_Record.xlsx) lists the actual phases and the open actions; target dates are left for management to set.

# Verification and approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by — Lead Engineer | Richard Watson Stephen Amudha | Richard Watson Stephen Amudha | 2026-10-07 |
| Reviewed by — EchoMind Project Lead | Alexander Peter | Alexander Peter | 2026-10-07 |
| Quality assurance — QA / MR | Sheryl Nazareth | Sheryl Nazareth | 2026-10-07 |
| Approved by — Managing Director | Anita Johan | Anita Johan | 2026-10-07 |

Signatures are the typed names of the role holders. Review and approval were confirmed by each of them on 2026-10-07 and are recorded in docs/qms/records/approvals/2026-10-07_AR-2026-001_document_approval.md (SOP-01 §6).