## Lessons
Lesson ID | Date | Area | Lesson | Reference | Action
LL-2026-01 | 2026-10-06 | Deployment | Hand deployments (`docker cp`) left the live code outside any image; a restart would have reverted a month of work. | NC-2026-011 | Snapshot taken; deploy only from built images (open).
LL-2026-02 | 2026-10-06 | Security / change control | A security setting (`AUTH_ENABLED`) changed in an untracked file with no record; the public instance ran ungated. | NC-2026-009 | Login restored; record runtime-setting changes in REG-07; external gate check (open).
LL-2026-03 | 2026-09-22 | Measurement | The evaluation corpus lived only in a mutable volume; its loss silently invalidated the quality instrument. | NC-2026-008 | Version-control a corpus manifest; pre-flight check (open).
LL-2026-04 | 2026-09-28 | QA process | Without CI, five stale tests and 20 type errors went unnoticed and a release was tagged with them failing. | NC-2026-010 | Fixed 5ddf8a6/736ea61; CI (open).
LL-2026-05 | 2026-10-06 | Platform | Sharing the GPU with another project causes speech-model start-up failures (CUDA OOM). | Observation | GPU sharing policy; CPU fallback flags exist.
LL-2026-06 | 2026-08-07 | Architecture | A per-path namespace control failed twice in the same way. | NC-2026-001/002 | Wrapper added; make filtering structural (open).
LL-2026-07 | 2026-09-04 | Suppliers | Depending on a moving upstream branch caused a build outage. | NC-2026-006 | Pinned to a verified commit (done).
LL-2026-08 | 2026-07-30 | Design decisions | A feature measured worse than baseline was switched off rather than rationalised. | NC-2026-005 | Measure before enabling (positive practice).
LL-2026-09 | 2026-09-21 | Reviews | 18 of 40 plausible review findings were wrong when verified; acting on them would have added defects. | RF-2026-001 | Verify findings before actioning (adopted).
LL-2026-10 | 2026-07-29 | Observability | Two controls failed silently (voice auth gate, null audio). | NC-2026-003/004 | Failure paths must produce a signal (SOP-12).
LL-2026-11 | 2026-08-07 | Claims | Published claims contradicted our own measurements. | NC-2026-007 | Measure before claiming (QP-01 §2.3).
LL-2026-12 | 2026-10-06 | Testing | API-level tests found four defects that the unit suites could not. | NC-2026-012…015 | Fixed; 14 regression tests added; API acceptance in CI (open).
LL-2026-13 | 2026-10-06 | Observability | A healthcheck that does not exercise the function it guards stayed green while embeddings failed. | NC-2026-016 | Healthcheck to perform a real embedding (open).
LL-2026-14 | 2026-10-06 | Change control | Re-testing after a fix found a regression the fix itself introduced (logout logged as anonymous). | QA-FAIL-2026-06 | Always re-run the full acceptance suite after a fix (adopted).
LL-2026-15 | 2026-04 | Client reviews | Off-the-shelf speech-to-speech systems (Kyutai Unmute, NVIDIA PersonaPlex) were either slow or could not use the customer's knowledge base; each client demonstration exposed it early. | EM26-18 CR-2026-03/04 | Show working versions to the client early; own dual-loop architecture adopted.
LL-2026-16 | 2026-03 | Large documents | A 7,300-page regulation (DoD FMR) needs structure-aware retrieval; BookRAG measured worse than section-based retrieval (43/52 vs 50/52). | EM26-18 AC-22; 2decb99 | Measure each retrieval method on the golden suite before adopting it.
LL-2026-17 | 2026-04 | Deployment | A unit taken to a client site may have no network; the hotspot makes it reachable, but its configuration lives only on the device. | EM26-18 CR-2026-05, AC-26 | Bring device configuration under version control.