## Project history
When | Event / requirement / feedback | Source | Review / action | Evidence
2025 | EchoMind (predecessor) delivered a live transcript and a chatbot with RAG on a PC we built for the client, as the client required | 2025 client project | — | 2025 evidence pack; EM26-00 §0
2026-01 | Portable AI supercomputers (NVIDIA DGX Spark) reach the market; the team decides to move the product to one | Management / engineering decision | CR-2026-01 | This log
2026-02 | First DGX Spark bought; the 2025 code ported in full and running on it | Engineering | AC-20 | 4b90b36, c751d79 (2026-02-05)
2026-03 | Requirements from Client A and Client B (Bahrain): (1) personal AI assistant, (2) conversation assistance, (3) financial knowledge base on the DoD Financial Management Regulation (DoD 7000.14-R) | Clients A and B | CR-2026-02 | 95d3512 (2026-03-08)
2026-03 | Conversation assistance v1 on the Kyutai Unmute stack — client: not natural and slow | Clients A and B | CR-2026-03 | 4b90b36 (Moshi adapter), bff6cf2 (Kyutai STT)
2026-03 | DoD FMR is a very large document: BookRAG and PageIndex tried; hierarchical (section → chunk) chunking adopted for performance | Engineering | AC-22 | 31f1205 … 5057a30 (2026-03-03 → 06); 23ac2f9 (03-07); 2decb99 (07-30)
2026-03 → 04 | Conversation assistance v2 on NVIDIA PersonaPlex — client: must work with the customer's large data in spoken conversation | Clients A and B | CR-2026-04 | QASC 2026 paper (539493f)
2026-04 | Own dual-loop conversation architecture built and pushed to the code | Engineering | AC-24 | ddc0aa3, d89aeda (2026-04-08)
2026-04 | Alexander Peter asks how a unit will work once deployed on a client site; proposes a hotspot — at every boot the unit raises its own Wi-Fi hotspot and serves a web page from which the applications open | Project Lead design review | CR-2026-05 | Deployment unit configuration; 0818cdc (2026-04-10)
2026-04 | Client A reports live-transcript accuracy and speed problems — better speech model with fallback across models; chat moved from Ollama to TensorRT-LLM | Client A | CR-2026-06 | d89aeda (04-08), b6a70d8 (06-26), 80375c6 (07-29)
2026-05 | Client C (law firm) likes conversation and live transcript; asks for a mode that listens, pulls up data while people speak and shows it on screen without replying — the Silent Assistant | Client C | CR-2026-07 | ec9b180 (05-11), f75121b (06-27), 7f2658a (08-16)
2026-05 | Group discussions: a diarisation model adopted after much trial and error in model selection — Boardroom | Engineering | CR-2026-08 | f540976 (05-14), cf463aa (05-19), e1a337b (05-27)
2026-06 | Client D (Gulf region) asks for a document studio — PPT and PDF created locally inside the application, with and without a template, with generated images | Client D | CR-2026-09 | 2d23f40 (06-20), 66356f9 (06-27)

## Review log
Review | Date | Deliverable | Review type | Performed by | Findings | Actions | Closed | Record
CR-2026-01 | 2026-01 | Platform for the next product generation | Management / engineering review of the 2025 appliance against new hardware | EchoMind team | A single-PC appliance limits capacity and portability; a portable AI supercomputer is now available | 1 | 1 | Decision recorded here; 4b90b36
CR-2026-02 | 2026-03 | Requirements — Client A; Client B (Bahrain) | Requirements review with the clients | EchoMind team with the clients | 3 requirements: personal AI assistant; conversation assistance; DoD FMR financial knowledge base | 2 | 2 | 95d3512, 18715c7
CR-2026-03 | 2026-03 | Conversation assistance v1 (Kyutai Unmute stack) | Client demonstration review | Clients A and B | Not natural; too slow | 1 | 1 | 4b90b36, bff6cf2
CR-2026-04 | 2026-03 → 04 | Conversation assistance v2 (NVIDIA PersonaPlex) | Client demonstration review | Clients A and B | Fast, but cannot use the customer's large knowledge base in spoken conversation | 1 | 1 | ddc0aa3; QASC 2026 paper
CR-2026-05 | 2026-04 | Field deployment of the unit | Design review | Alexander Peter (EchoMind Project Lead) | No way to reach a deployed unit on a site without a network | 2 | 1 | Deployment unit; 0818cdc
CR-2026-06 | 2026-04 | Live transcription | Client feedback review | Client A | Accuracy and speed below need (e.g. 'DoD FMR' heard as 'DODFMA') | 3 | 3 | d89aeda, b6a70d8, 80375c6
CR-2026-07 | 2026-05 | Conversation and live transcript demonstration | Client review | Client C (law firm) | Needs a listen-only assistant that pulls supporting data onto the screen while people speak | 2 | 2 | ec9b180, f75121b, 7f2658a
CR-2026-08 | 2026-05 | Group discussions (Boardroom) | Design review and model trials | EchoMind team | Speaker separation (diarisation) needed; model chosen by trial | 2 | 2 | f540976, cf463aa, e1a337b
CR-2026-09 | 2026-06 | Document creation | Client requirement review | Client D (Gulf region) | PPT and PDF made locally, with and without a template, with images | 1 | 1 | 2d23f40, 66356f9
RV-2026-01 | 2026-07-29 → 08-07 | Retrieval pipeline | Golden-question evaluation (52 questions) against the live stack | Richard Watson Stephen Amudha | 5 defects + 1 isolation regression | 2 | 2 | ebd232f, 4e27109 — REG-10 RF-2026-003
RV-2026-02 | 2026-08-07 | Research paper experiment campaign (E1–E10) | Measurements checked against the paper's own claims | Richard Watson Stephen Amudha | 4 substantive (2 contradict published claims) | 1 | 0 | eval/paper/results/SUMMARY.json — RF-2026-002
RV-2026-03 | 2026-09-21 | Voice change set (speculative reply, tool routing, GPU STT) | Structured adversarial review, five lenses, each finding independently verified | Richard Watson Stephen Amudha (AI-assisted, independent verification) | 40 raised; 22 confirmed; 18 refuted | 22 | 22 | ff29843 — RF-2026-001
RV-2026-04 | 2026-09-22 | Golden evaluation re-run for audit evidence | Measurement review | Richard Watson Stephen Amudha | Corpus absent (9/52) | 2 | 1 | NC-2026-008; eval_20260922-135322.json
RV-2026-05 | 2026-09-28 | Repository health check | Unit suites + type-check against HEAD | Richard Watson Stephen Amudha | 5 failing tests, 20 type errors | 2 | 2 | 5ddf8a6, 736ea61 — NC-2026-010
RV-2026-06 | 2026-10-06 | October audit pack | Every claim re-verified against the running system | Richard Watson Stephen Amudha | 6 statements wrong (incl. no login on the public site) | 2 | 2 | 855bd80, 1d7f154 — NC-2026-009
RV-2026-07 | 2026-10-06 | Release candidate (13 acceptance test cases) | Executed acceptance tests, 4 runs | Richard Watson Stephen Amudha | 4 defects; re-tests found 2 more | 5 | 3 | e0ed4d0, 3feb5db, f1b8445 — NC-2026-012…016
RV-2026-08 | 2026-10-07 | Public instance access logs | Log review for the ungated period | Richard Watson Stephen Amudha | Ungated 68 days; 64 scanner probes; no data change outside engineering work | 4 | 2 | records/capa/2026-10-07_NC-2026-009_access_log_review.md

## Action log
Action | From | Action | Owner | Due | Status | Closure evidence | Ticket
AC-20 | CR-2026-01 | Buy the first DGX Spark and port the 2025 code to it (ARM64) | EchoMind team | 2026-02 | Closed | 4b90b36, c751d79 (2026-02-05) — 2025 code running on the DGX Spark | —
AC-21 | CR-2026-02 | Personal AI assistant: financial-assistant behaviour, conversation memory, personas | Richard Watson Stephen Amudha | 2026-04 | Closed | 95d3512, e59fd55 (2026-03-08); 518fb8e (2026-04-08); c6b834d (2026-06-27) | —
AC-22 | CR-2026-02 | DoD FMR knowledge base: try BookRAG and PageIndex; adopt hierarchical section → chunk retrieval with table-of-contents routing and regulation-tuned query classification | Richard Watson Stephen Amudha | 2026-03 | Closed | 31f1205, 045b1b1 (03-03); 18715c7, cfe3360 (03-05); 5057a30 (03-06). BookRAG 23ac2f9 (03-07) measured 43/52 vs 50/52 and was switched off (2decb99, 07-30); PageIndex evaluated, not adopted | —
AC-23 | CR-2026-03 | Replace the Unmute stack with NVIDIA PersonaPlex | Richard Watson Stephen Amudha | 2026-03 | Closed — superseded by AC-24 | Trial compared in the QASC 2026 paper; trial code not kept | —
AC-24 | CR-2026-04 | Build our own dual-loop conversation architecture grounded in the customer's knowledge base | Richard Watson Stephen Amudha | 2026-04 | Closed | ddc0aa3, d89aeda (04-08); fbbadd0 (05-28); 5ce8bbe, cbc57d1 (08-07) — 636 ms median first audio vs 866 ms single loop | —
AC-25 | CR-2026-05 | Hotspot: unit raises a Wi-Fi hotspot at every boot and serves a landing page that opens the applications | Alexander Peter | 2026-04 | Closed | Built on the deployment unit; offline preparation 0818cdc (2026-04-10) | —
AC-26 | CR-2026-05 | Bring the hotspot configuration under version control and add it to the deployment guide | Alexander Peter | 2026-10-31 | Open | — | —
AC-27 | CR-2026-06 | Replace Whisper with Nemotron streaming speech recognition for live transcription | Richard Watson Stephen Amudha | 2026-04-08 | Closed | d89aeda, 172b94c, ddc0aa3 | —
AC-28 | CR-2026-06 | Accurate final transcript with Parakeet-TDT and automatic fallback to the streaming model | Richard Watson Stephen Amudha | 2026-06-26 | Closed | b6a70d8, 3a6b1f9 — fixes 'DoD FMR' → 'DODFMA' | —
AC-29 | CR-2026-06 | Move chat generation from Ollama to TensorRT-LLM for speed | Richard Watson Stephen Amudha | 2026-07-29 | Closed | 06e788a (03-20) integration; 80375c6 (07-29) Qwen3-30B-A3B NVFP4 on TensorRT-LLM; Ollama kept for embeddings and rollback | —
AC-30 | CR-2026-07 | Silent Assistant: runs with the live transcript; an assistant and an agent check the content continuously and surface data and pointers on screen without replying | Richard Watson Stephen Amudha | 2026-05-11 | Closed | ec9b180 (2026-05-11) | —
AC-31 | CR-2026-07 | Law rule pack, always-surface mode, namespace awareness; sentence-level checks with quoted proof | Richard Watson Stephen Amudha | 2026-08-16 | Closed | f75121b (06-27), 7f2658a (08-16) | —
AC-32 | CR-2026-08 | Select a diarisation model by trial; build Boardroom (group discussion, speaker-separated transcript, report) | Richard Watson Stephen Amudha | 2026-05-27 | Closed | f540976 (05-14), cf463aa (05-19), e1a337b (05-27); VibeVoice-ASR adopted (REG-02 M-06) | —
AC-33 | CR-2026-08 | Harden Boardroom: report salvage when the model output is truncated | Richard Watson Stephen Amudha | 2026-09-04 | Closed | b08cf25 (06-18), 724fb98 (09-04) | —
AC-34 | CR-2026-09 | Evaluate image-generation and document models; build Document Studio with PDF and PPTX export, on-device images, with and without a template | Richard Watson Stephen Amudha | 2026-06-27 | Closed | 2d23f40 (06-20), 66356f9 (06-27); SDXL-Turbo on device (REG-02) | —
AC-01 | RV-2026-01 | Enforce namespace predicate on the sparse transcript path; audit all paths | Richard Watson Stephen Amudha | 2026-08-07 | Closed | 4e27109 — 0/359 out-of-namespace hits | —
AC-02 | RV-2026-01 | Fix five retrieval defects found by the golden suite | Richard Watson Stephen Amudha | 2026-07-29 | Closed | ebd232f — suite restored to 49/52 | —
AC-03 | RV-2026-02 | Record contradicting findings verbatim; correct the claims in the next paper version | Richard Watson Stephen Amudha | Next version | Open (recording done) | SUMMARY.json | #19, #27
AC-04 | RV-2026-03 | 22 confirmed voice findings fixed before release (e.g. abort blocking the event loop; WebSocket close not aborting generation; hold phrase racing the answer; mid-word text split) | Richard Watson Stephen Amudha | 2026-09-21 | Closed | ff29843 — 12/12 spoken turns, barge-in verified, 0 CUDA errors | —
AC-05 | RV-2026-04 | Make the evaluation abort when its corpus is missing | Richard Watson Stephen Amudha | 2026-10-07 | Closed | f3aca50 — aborts listing 15 documents | #48
AC-06 | RV-2026-04 | Restore the evaluation corpus and re-measure | Richard Watson Stephen Amudha | 2026-10-13 | Open | — | #47
AC-07 | RV-2026-05 | Correct stale tests and type errors | Richard Watson Stephen Amudha | 2026-09-28 | Closed | 5ddf8a6, 736ea61 | —
AC-08 | RV-2026-05 | Run the suites automatically on every push (CI) | Richard Watson Stephen Amudha | 2026-10-07 | Closed | CI runs 37561379960 (pass) / 37561804619 (fails on broken test) | #50
AC-09 | RV-2026-06 | Restore application login on the public instance | Richard Watson Stephen Amudha | 2026-10-06 | Closed | Externally verified 401 | #29
AC-10 | RV-2026-06 | Correct the audit pack and registers against the running system | Richard Watson Stephen Amudha | 2026-10-06 | Closed | 855bd80, 1d7f154 | #40
AC-11 | RV-2026-07 | Logout revokes tokens; upload allow-list; small-talk routing; export key formats | Richard Watson Stephen Amudha | 2026-10-06 | Closed | e0ed4d0 + 14 regression tests; run 4 pass | #32–#35
AC-12 | RV-2026-07 | Activity log identifies the caller before logout revokes the token | Richard Watson Stephen Amudha | 2026-10-06 | Closed | 3feb5db; run 4 AC-101.8 pass | #32
AC-13 | RV-2026-07 | Embedding service on CPU; healthcheck makes a real embedding | Richard Watson Stephen Amudha | 2026-10-07 | Closed | DC-2026-005; f3aca50 | #59
AC-14 | RV-2026-07 | Decide the GPU-sharing policy for the host | Anita Johan | 2026-10-31 | Open | — | #60
AC-15 | RV-2026-07 | Sign the v1.4.0 and v1.4.1 release records | Anita Johan | 2026-10-13 | Open | — | #61
AC-16 | RV-2026-08 | External login check every 6 hours | Richard Watson Stephen Amudha | 2026-10-07 | Closed | run 37561803121 | #51
AC-17 | RV-2026-08 | Record runtime-setting changes (SOP-06 §10.1, drift check) | Richard Watson Stephen Amudha | 2026-10-07 | Closed | f3aca50 | #52
AC-18 | RV-2026-08 | Confirm the 2026-08-07 / 08-16 / 09-15 knowledge-base operations were internal; check Cloudflare analytics | Kishan Haravu Pradeep | 2026-10-13 | Open | — | #53 follow-up
AC-19 | RV-2026-08 | Record the real client address (CF-Connecting-IP) in the activity log; retain proxy logs | Richard Watson Stephen Amudha | 2026-10-31 | Open | — | —