## Document control
EM26-20 — Functional Requirements Register (2025 → 2026)
AJACE Inc. · EchoMind Product · ISO 9001:2015 evidence · Controlled in docs/qms (git); uncontrolled when printed
Field | Entry
Document ID | EM26-20
Title | Functional Requirements Register (2025 → 2026)
Version | 1.1
Date | 2026-10-12
Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA
Area / project | EchoMind Product — EchoMind (2025 pilot appliance) and EchoMind Enterprise (2026, repository RW2523/echomind-enterprise)
Status | APPROVED — rev 1.1 2026-10-12 (AR-2026-004); rev 1.0 2026-10-12 (AR-2026-003)
Purpose | The functional requirements of EchoMind — the 2025 appliance baseline and the 2026 EchoMind Enterprise requirements — with their source, the review that raised them, when they were delivered (commit), how they were verified and in which release.
Sources | 2025 SOW and test cases; 2026 client and design reviews (EM26-19); git history; acceptance test run 4 (2026-10-06); CAPABILITIES.md.
Copy | PUBLIC COPY — clients shown as Client A–D; the controlled copy given to the auditor carries the names
Dating rule | Every date comes from a record: a 2025 minute or review document, a git commit, a register entry or a test run. Where a remembered month and the commit record differed, the commit date is used. Nothing is back-dated.
Sheet | What it holds
FR register | Every functional requirement with source, priority, status, delivery, first version and verification
Traceability | Requirement → review → delivery commit → version → test → release
Requirement changes | Changes to requirements and why (ISO 9001 8.2.4)
Summary | Counts by module and status (live formulas)
Role | Name | Signature | Date
Prepared by — Lead Engineer | Richard Watson Stephen Amudha | Richard Watson Stephen Amudha | 2026-10-12
Reviewed by — EchoMind Project Lead | Alexander Peter | Alexander Peter | 2026-10-12
Quality assurance — QA / MR | Sheryl Nazareth | Sheryl Nazareth | 2026-10-12
Approved by — Managing Director | Anita Johan | Anita Johan | 2026-10-12
Approval record
Rev 1.1: docs/qms/records/approvals/2026-10-12_AR-2026-004_register_revision_approval.md; rev 1.0: …/2026-10-12_AR-2026-003_register_approval.md. Review and approval confirmed by each role holder; signatures are their typed names (SOP-01 §6).
Date | Version | Owner | Change
2026-10-11 | 1.0 | Richard Watson Stephen Amudha (Lead Engineer) | First issue
2026-10-12 | 1.0 | Anita Johan (Managing Director) | Approved — AR-2026-003
2026-10-12 | 1.1 | Richard Watson Stephen Amudha (Lead Engineer) | Versions v1.0.0–v1.4.1 added (v1.0.0–v1.3.0 retrospective baselines, REG-08 §2a); version reviews
2026-10-12 | 1.1 | Anita Johan (Managing Director) | Approved — AR-2026-004

## FR register
Functional requirements — 2025 baseline and 2026
Priority: Must / Should / Could. ‘First version’ is the version (REG-08) that first contained the requirement; ‘Verified in’ the release whose tests verified it.
FR ID | Module | Requirement | Source | Raised | Raised in review | Priority | Status | First delivered (commit) | First version | Current implementation | Verified by | Verified in
FR-2025-01 | 2025 appliance | Chat with a local LLM through a web interface | SOW — 2025 university pilot customer | 2025-05-22 | DR-2025-03 | Must | Delivered | 2025-09 (llama3.1:8b, Streamlit UI) | 2025 appliance | Carried into FR-KC-02 / FR-KC-03 | 2025 Test case 1 — UI loading and basic LLM query | 2025 appliance
FR-2025-02 | 2025 appliance | Real-time transcription with contextual questions over the transcript | SOW — 2025 university pilot customer | 2025-05-22 | DR-2025-03 | Must | Delivered | 2025-09 | 2025 appliance | Carried into FR-LT-01 / FR-LT-03 | 2025 Test case 2; TC-EM-Transcribe-003 | 2025 appliance
FR-2025-03 | 2025 appliance | Upload documents into the knowledge base, with an activity record | SOW — 2025 university pilot customer | 2025-07-15 | DR-2025-07 | Must | Delivered | 2025-09 | 2025 appliance | Carried into FR-KC-01 | TC-EM-UI-Upload-001 | 2025 appliance
FR-2025-04 | 2025 appliance | Containerised service stack (api, ui, vectordb, transcribe, ollama), deployable on site | SOW — 2025 university pilot customer | 2025-07-15 | DR-2025-07 | Must | Delivered | 2025-09 (Portainer stacks) | 2025 appliance | Carried into FR-PL-01 (Docker Compose) | TC-EM-Stacks-002 | 2025 appliance
FR-2025-05 | 2025 appliance | System guide and maintenance manual for the customer | SOW — 2025 university pilot customer | 2025-08-05 | DR-2025-09 | Should | Delivered (2026) | 2026-06-22 USER_MANUAL (dfcf300) | v1.2.0 | docs/USER_MANUAL.md / .pdf | Document review | v1.4.0
FR-PL-01 | Platform | Run the whole product offline on one portable AI supercomputer (DGX Spark) | CR-2026-01 platform decision | 2026-01 | CR-2026-01 | Must | Delivered | 2026-02-05 (4b90b36, c751d79) | v1.0.0 | Offline preparation 0818cdc; offline bundle scripts | TC-EM-OPS-105; Pass (run 4, 2026-10-06) | v1.4.0
FR-KC-01 | Knowledge chat | Upload PDF, DOCX and PPTX and index them for questions | 2025 baseline (FR-2025-03) | 2026-02-05 | CR-2026-02 | Must | Delivered | 2026-02-05 (4b90b36) | v1.0.0 | Ingestion overhaul 7e582e1 (2026-08-16); allow-list e0ed4d0 | TC-EM-DOC-102 — Pass (run 4, 2026-10-06) | v1.4.1
FR-KC-02 | Knowledge chat | Answer from the customer's documents with citations; never invent a source | 2025 baseline (FR-2025-01) | 2026-02-05 | CR-2026-02 | Must | Delivered | 2026-02-05 (4b90b36) | v1.0.0 | Honest citations 343117f (2026-07-29) | TC-EM-RAG-103 — Pass (run 4, 2026-10-06); golden suite | v1.4.1
FR-KC-03 | Knowledge chat | Stream answers token by token | 2025 baseline (FR-2025-01) | 2026-02-05 | — | Should | Delivered | 2026-02-05 (da4787d) | v1.0.0 | TensorRT-LLM streaming | Unit tests (CI) | v1.4.0
FR-KC-04 | Knowledge chat | Find answers in very large regulations (DoD FMR, ~7,300 pages) by section and table of contents | Client A; Client B (Bahrain) | 2026-03 | CR-2026-02 | Must | Delivered | 2026-03-05 (18715c7, cfe3360); TOC 5057a30 (03-06) | v1.1.0 | Hierarchical section → chunk retrieval; BookRAG off (2decb99) | Golden suite 50/52 (2026-07-30) | v1.4.0
FR-KC-05 | Knowledge chat | Personas (financial adviser, lawyer, teacher and others) | Client A; Client B (Bahrain) — personal AI assistant | 2026-03 | CR-2026-02 | Should | Delivered | 2026-03-08 (95d3512) | v1.1.0 | Persona types 518fb8e (04-08); per-vertical personas c6b834d (06-27) | Manual check; persona quality overhaul 343117f | v1.4.0
FR-KC-06 | Knowledge chat | Remember the conversation across turns | Internal | 2026-02-06 | — | Should | Delivered | 2026-02-06 (341b0be) | v1.0.0 | Follow-up context b6aa963 (07-29) | Golden suite multi-turn items | v1.4.0
FR-KC-07 | Knowledge chat | Separate knowledge bases per vertical / tenant; no cross-tenant answers | Vertical packs | 2026-06-27 | RV-2026-01 | Must | Delivered | 2026-06-27 (2dba137, ef19d68) | v1.2.0 | Namespace predicate on all paths 4e27109 (08-07) | TC-EM-ISO-104 — Pass (run 4, 2026-10-06) | v1.4.1
FR-KC-08 | Knowledge chat | Manage chats (list, rename, delete) | Internal | 2026-03-09 | — | Could | Delivered | 2026-03-09 (2b9730b) | v1.1.0 | — | Manual check | v1.4.0
FR-LT-01 | Live transcription | Show a live transcript while people speak | 2025 baseline (FR-2025-02) | 2026-02-05 | CR-2026-06 | Must | Delivered | 2026-02-05 (4b90b36) | v1.0.0 | Nemotron streaming ASR (d89aeda, 04-08) | TC-EM-TRN-112 — Not executed (run 4, 2026-10-06) — manual test outstanding | v1.4.1
FR-LT-02 | Live transcription | Accurate final transcript for domain terms, with automatic fallback to the streaming model | Client A | 2026-04 | CR-2026-06 | Must | Delivered | 2026-06-26 (b6a70d8, 3a6b1f9) | v1.2.0 | Parakeet-TDT final, Nemotron partials | Voice end-to-end test 8e6d984; unit tests | v1.4.0
FR-LT-03 | Live transcription | Store transcripts into the knowledge base automatically | 2025 baseline (FR-2025-02) | 2026-02-27 | — | Should | Delivered | 2026-02-27 (223714c) | v1.0.0 | Auto-store every 60 s | Unit tests | v1.4.0
FR-LT-04 | Live transcription | Word cloud of the live conversation | Internal | 2026-03-09 | — | Could | Delivered | 2026-03-09 (5d64088) | v1.1.0 | — | Manual check | v1.4.0
FR-SA-01 | Silent Assistant | Listen during a conversation and put supporting data on screen without speaking | Client C (law firm) | 2026-05 | CR-2026-07 | Must | Delivered | 2026-05-11 (ec9b180) | v1.2.0 | Always-surface mode f75121b (06-27) | Unit tests; scenario harness | v1.4.0
FR-SA-02 | Silent Assistant | Rule packs per vertical (law and others) | Client C (law firm) | 2026-05 | CR-2026-07 | Should | Delivered | 2026-06-27 (f75121b) | v1.2.0 | — | Unit tests | v1.4.0
FR-SA-03 | Silent Assistant | Check each sentence and show quoted proof from the documents | Client C (law firm) | 2026-05 | CR-2026-07 | Should | Delivered | 2026-08-16 (7f2658a) | v1.3.0 | Gated checks 15f3c96 (09-14) | Scenario harness (silent-assistant v2) | v1.4.0
FR-BR-01 | Boardroom | Record a meeting and produce a speaker-separated transcript | Internal (group discussions) | 2026-05 | CR-2026-08 | Must | Delivered | 2026-05-14 (f540976); 05-19 cf463aa | v1.2.0 | VibeVoice-ASR in an isolated process; Nemotron fallback | TC-EM-BRD-111 — Pass (run 4, 2026-10-06) | v1.4.1
FR-BR-02 | Boardroom | Generate a meeting report and export it as PDF or PPTX | Internal (group discussions) | 2026-05 | CR-2026-08 | Must | Delivered | 2026-05-14 (f540976) | v1.2.0 | Report salvage 724fb98 (09-04) | TC-EM-BRD-111 — Pass (run 4, 2026-10-06) | v1.4.1
FR-VC-01 | Voice | Natural spoken conversation grounded in the customer's knowledge base | Client A; Client B (Bahrain) | 2026-03 | CR-2026-04 | Must | Delivered | 2026-04-08 (ddc0aa3) — own dual loop | v1.1.0 | Speculative replies ff29843 (09-21) | Paper E4/E7 (2026-08-07); 12 spoken turns (09-21) | v1.4.0
FR-VC-02 | Voice | Interrupt the assistant by speaking (barge-in) | Client A; Client B (Bahrain) | 2026-03 | CR-2026-03 | Must | Delivered | 2026-02-06 (65e01ec) | v1.0.0 | Tuned 5088c93 (06-26) | Paper E7: success 1.00; stop time 2.13 s (NFR-P07 open) | v1.4.0
FR-VC-03 | Voice | Personal assistant: wake word, listen-only mode, memory of what was said | Client A; Client B (Bahrain) — personal AI assistant | 2026-03 | CR-2026-02 | Should | Delivered | 2026-02-25 (e0ca515, a1fd76b) — available before the request | v1.0.0 | Financial-assistant behaviour 95d3512 (03-08) | Manual check | v1.4.0
FR-VC-04 | Voice | Choice of voices and TTS engine | Internal | 2026-06-27 | — | Could | Delivered | 2026-06-27 (52e6db9, 4bc0d58) | v1.2.0 | Piper default; Kokoro optional | Manual check | v1.4.0
FR-DS-01 | Document Studio | Create documents from a topic, a chat or uploaded documents | Client D (Gulf region) | 2026-06 | CR-2026-09 | Must | Delivered | 2026-06-20 (2d23f40) | v1.2.0 | — | TC-EM-DGEN-110 — Pass (run 4, 2026-10-06) | v1.4.1
FR-DS-02 | Document Studio | Export as PDF and PPTX, made locally | Client D (Gulf region) | 2026-06 | CR-2026-09 | Must | Delivered | 2026-06-20 (2d23f40) | v1.2.0 | — | TC-EM-DGEN-110 — Pass (run 4, 2026-10-06) | v1.4.1
FR-DS-03 | Document Studio | Generated images, made on the device | Client D (Gulf region) | 2026-06 | CR-2026-09 | Should | Delivered | 2026-06-20 (2d23f40) — SDXL-Turbo | v1.2.0 | — | Manual check (image status endpoint) | v1.4.0
FR-DS-04 | Document Studio | Work with or without a template; upload your own template | Client D (Gulf region) | 2026-06 | CR-2026-09 | Should | Delivered | 2026-06-27 (66356f9) | v1.2.0 | 18 built-in templates + custom upload | TC-EM-DGEN-110 — Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-02 | Platform | Login, roles and admin user management | Internal (security) | 2026-06-27 | SR-2026-01 | Must | Delivered | 2026-06-27 (c9bad3d, d12db42, 7a83262) | v1.2.0 | Logout revokes tokens e0ed4d0 | TC-EM-AUTH-101 — Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-03 | Platform | Activity log of who did what | Internal (security) | 2026-06-27 | — | Must | Delivered | 2026-06-27 (ac26d41) | v1.2.0 | Caller identified before the request 3feb5db | TC-EM-AUTH-101 — Pass (run 4, 2026-10-06) (AC-101.8) | v1.4.1
FR-PL-04 | Platform | Export gateway that finds and redacts personal data and keys before content leaves | Product vision (offline → online) | 2026-06-27 | — | Must | Delivered | 2026-06-27 (d19177d) | v1.2.0 | Key formats e0ed4d0 | TC-EM-EXP-108 — Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-05 | Platform | Vertical packs (banking, health, law, meetings, retail) | Client verticals | 2026-06-27 | — | Should | Delivered | 2026-06-27 (e8ead2f, c6b834d) | v1.2.0 | — | Manual check | v1.4.0
FR-PL-06 | Platform | Reach a deployed unit on site with no network: hotspot and landing page at boot | Alexander Peter (Project Lead) | 2026-04 | CR-2026-05 | Must | Delivered | 2026-04 — on the deployment unit | v1.1.0 | Configuration not yet in the repository (AC-26) | Demonstrated on the unit; record to be added (AC-26) | Deployment unit
FR-PL-07 | Platform | Public reference instance for demonstrations | Internal | 2026-06-24 | — | Should | Delivered | 2026-06-24 (7c521f3) | v1.2.0 | Login enforced; checked every 6 h | External gate check (every 6 h) | v1.4.1
FR-PL-08 | Platform | Report the running version and commit | QMS (G-01) | 2026-09-21 | RV-2026-06 | Must | Delivered | 2026-09-22 (51fd3bc) | v1.4.0 | /api/version, voice /health, /build.json | TC-EM-REL-106 — Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-09 | Platform | Back up and restore customer data | QMS (G-03); 2025 lesson #18 | 2026-09-21 | RV-2026-06 | Must | Delivered | 2026-09-22 (backup_data.sh, restore_data.sh) | v1.4.0 | Nightly off-host copy to be installed (R-02) | TC-EM-BKP-113 — Pass (run 4, 2026-10-06) | v1.4.0

## Traceability
Traceability — requirement → review → delivery → verification → release
FR ID | Requirement | Review | Delivered | First version | Verification | Result | Verified in
FR-2025-01 | Chat with a local LLM through a web interface | DR-2025-03 | 2025-09 (llama3.1:8b, Streamlit UI) | 2025 appliance | 2025 Test case 1 | UI loading and basic LLM query | 2025 appliance
FR-2025-02 | Real-time transcription with contextual questions over the transcript | DR-2025-03 | 2025-09 | 2025 appliance | 2025 Test case 2; TC-EM-Transcribe-003 | See verification | 2025 appliance
FR-2025-03 | Upload documents into the knowledge base, with an activity record | DR-2025-07 | 2025-09 | 2025 appliance | TC-EM-UI-Upload-001 | See verification | 2025 appliance
FR-2025-04 | Containerised service stack (api, ui, vectordb, transcribe, ollama), deployable on site | DR-2025-07 | 2025-09 (Portainer stacks) | 2025 appliance | TC-EM-Stacks-002 | See verification | 2025 appliance
FR-2025-05 | System guide and maintenance manual for the customer | DR-2025-09 | 2026-06-22 USER_MANUAL (dfcf300) | v1.2.0 | Document review | See verification | v1.4.0
FR-PL-01 | Run the whole product offline on one portable AI supercomputer (DGX Spark) | CR-2026-01 | 2026-02-05 (4b90b36, c751d79) | v1.0.0 | TC-EM-OPS-105; Pass (run 4, 2026-10-06) | See verification | v1.4.0
FR-KC-01 | Upload PDF, DOCX and PPTX and index them for questions | CR-2026-02 | 2026-02-05 (4b90b36) | v1.0.0 | TC-EM-DOC-102 | Pass (run 4, 2026-10-06) | v1.4.1
FR-KC-02 | Answer from the customer's documents with citations; never invent a source | CR-2026-02 | 2026-02-05 (4b90b36) | v1.0.0 | TC-EM-RAG-103 | Pass (run 4, 2026-10-06); golden suite | v1.4.1
FR-KC-03 | Stream answers token by token | — | 2026-02-05 (da4787d) | v1.0.0 | Unit tests (CI) | See verification | v1.4.0
FR-KC-04 | Find answers in very large regulations (DoD FMR, ~7,300 pages) by section and table of contents | CR-2026-02 | 2026-03-05 (18715c7, cfe3360); TOC 5057a30 (03-06) | v1.1.0 | Golden suite 50/52 (2026-07-30) | See verification | v1.4.0
FR-KC-05 | Personas (financial adviser, lawyer, teacher and others) | CR-2026-02 | 2026-03-08 (95d3512) | v1.1.0 | Manual check; persona quality overhaul 343117f | See verification | v1.4.0
FR-KC-06 | Remember the conversation across turns | — | 2026-02-06 (341b0be) | v1.0.0 | Golden suite multi-turn items | See verification | v1.4.0
FR-KC-07 | Separate knowledge bases per vertical / tenant; no cross-tenant answers | RV-2026-01 | 2026-06-27 (2dba137, ef19d68) | v1.2.0 | TC-EM-ISO-104 | Pass (run 4, 2026-10-06) | v1.4.1
FR-KC-08 | Manage chats (list, rename, delete) | — | 2026-03-09 (2b9730b) | v1.1.0 | Manual check | See verification | v1.4.0
FR-LT-01 | Show a live transcript while people speak | CR-2026-06 | 2026-02-05 (4b90b36) | v1.0.0 | TC-EM-TRN-112 | Not executed (run 4, 2026-10-06) | v1.4.1
FR-LT-02 | Accurate final transcript for domain terms, with automatic fallback to the streaming model | CR-2026-06 | 2026-06-26 (b6a70d8, 3a6b1f9) | v1.2.0 | Voice end-to-end test 8e6d984; unit tests | See verification | v1.4.0
FR-LT-03 | Store transcripts into the knowledge base automatically | — | 2026-02-27 (223714c) | v1.0.0 | Unit tests | See verification | v1.4.0
FR-LT-04 | Word cloud of the live conversation | — | 2026-03-09 (5d64088) | v1.1.0 | Manual check | See verification | v1.4.0
FR-SA-01 | Listen during a conversation and put supporting data on screen without speaking | CR-2026-07 | 2026-05-11 (ec9b180) | v1.2.0 | Unit tests; scenario harness | See verification | v1.4.0
FR-SA-02 | Rule packs per vertical (law and others) | CR-2026-07 | 2026-06-27 (f75121b) | v1.2.0 | Unit tests | See verification | v1.4.0
FR-SA-03 | Check each sentence and show quoted proof from the documents | CR-2026-07 | 2026-08-16 (7f2658a) | v1.3.0 | Scenario harness (silent-assistant v2) | See verification | v1.4.0
FR-BR-01 | Record a meeting and produce a speaker-separated transcript | CR-2026-08 | 2026-05-14 (f540976); 05-19 cf463aa | v1.2.0 | TC-EM-BRD-111 | Pass (run 4, 2026-10-06) | v1.4.1
FR-BR-02 | Generate a meeting report and export it as PDF or PPTX | CR-2026-08 | 2026-05-14 (f540976) | v1.2.0 | TC-EM-BRD-111 | Pass (run 4, 2026-10-06) | v1.4.1
FR-VC-01 | Natural spoken conversation grounded in the customer's knowledge base | CR-2026-04 | 2026-04-08 (ddc0aa3) — own dual loop | v1.1.0 | Paper E4/E7 (2026-08-07); 12 spoken turns (09-21) | See verification | v1.4.0
FR-VC-02 | Interrupt the assistant by speaking (barge-in) | CR-2026-03 | 2026-02-06 (65e01ec) | v1.0.0 | Paper E7: success 1.00; stop time 2.13 s (NFR-P07 open) | See verification | v1.4.0
FR-VC-03 | Personal assistant: wake word, listen-only mode, memory of what was said | CR-2026-02 | 2026-02-25 (e0ca515, a1fd76b) — available before the request | v1.0.0 | Manual check | See verification | v1.4.0
FR-VC-04 | Choice of voices and TTS engine | — | 2026-06-27 (52e6db9, 4bc0d58) | v1.2.0 | Manual check | See verification | v1.4.0
FR-DS-01 | Create documents from a topic, a chat or uploaded documents | CR-2026-09 | 2026-06-20 (2d23f40) | v1.2.0 | TC-EM-DGEN-110 | Pass (run 4, 2026-10-06) | v1.4.1
FR-DS-02 | Export as PDF and PPTX, made locally | CR-2026-09 | 2026-06-20 (2d23f40) | v1.2.0 | TC-EM-DGEN-110 | Pass (run 4, 2026-10-06) | v1.4.1
FR-DS-03 | Generated images, made on the device | CR-2026-09 | 2026-06-20 (2d23f40) — SDXL-Turbo | v1.2.0 | Manual check (image status endpoint) | See verification | v1.4.0
FR-DS-04 | Work with or without a template; upload your own template | CR-2026-09 | 2026-06-27 (66356f9) | v1.2.0 | TC-EM-DGEN-110 | Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-02 | Login, roles and admin user management | SR-2026-01 | 2026-06-27 (c9bad3d, d12db42, 7a83262) | v1.2.0 | TC-EM-AUTH-101 | Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-03 | Activity log of who did what | — | 2026-06-27 (ac26d41) | v1.2.0 | TC-EM-AUTH-101 | Pass (run 4, 2026-10-06) (AC-101.8) | v1.4.1
FR-PL-04 | Export gateway that finds and redacts personal data and keys before content leaves | — | 2026-06-27 (d19177d) | v1.2.0 | TC-EM-EXP-108 | Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-05 | Vertical packs (banking, health, law, meetings, retail) | — | 2026-06-27 (e8ead2f, c6b834d) | v1.2.0 | Manual check | See verification | v1.4.0
FR-PL-06 | Reach a deployed unit on site with no network: hotspot and landing page at boot | CR-2026-05 | 2026-04 — on the deployment unit | v1.1.0 | Demonstrated on the unit; record to be added (AC-26) | See verification | Deployment unit
FR-PL-07 | Public reference instance for demonstrations | — | 2026-06-24 (7c521f3) | v1.2.0 | External gate check (every 6 h) | See verification | v1.4.1
FR-PL-08 | Report the running version and commit | RV-2026-06 | 2026-09-22 (51fd3bc) | v1.4.0 | TC-EM-REL-106 | Pass (run 4, 2026-10-06) | v1.4.1
FR-PL-09 | Back up and restore customer data | RV-2026-06 | 2026-09-22 (backup_data.sh, restore_data.sh) | v1.4.0 | TC-EM-BKP-113 | Pass (run 4, 2026-10-06) | v1.4.0

## Requirement changes
Requirement changes (ISO 9001 8.2.4)
Change ID | Date | Requirements | Change | Review | Requested by | Status
RC-2025-01 | 2025-08-05 | FR-2025-01…04 | Requirements fixed in the signed SOW (offline on-premises system, BYOA pilot) | DR-2025-09 | 2025 university pilot customer; AJACE | SOW signed
RC-2026-01 | 2026-01 | FR-PL-01 | Platform changed from a single RTX 4090 PC to a DGX Spark | CR-2026-01 | EchoMind team | Implemented 2026-02-05
RC-2026-02 | 2026-03 | FR-VC-01 | Conversation must be natural and fast — Unmute stack replaced by PersonaPlex | CR-2026-03 | Clients A and B | Implemented; superseded by RC-2026-03
RC-2026-03 | 2026-04 | FR-VC-01 | Conversation must use the customer's large knowledge base — own dual-loop architecture | CR-2026-04 | Clients A and B | Implemented 2026-04-08
RC-2026-04 | 2026-03 → 07 | FR-KC-04 | DoD FMR retrieval: BookRAG and PageIndex tried; section-based retrieval kept; BookRAG switched off as it measured worse (43/52 vs 50/52) | CR-2026-02 | EchoMind team | Implemented 2026-07-30 (2decb99)
RC-2026-05 | 2026-04 | FR-LT-01, FR-LT-02 | Transcript accuracy and speed: Whisper → Nemotron; Parakeet final with fallback; chat Ollama → TensorRT-LLM | CR-2026-06 | Client A | Implemented 2026-04-08 → 07-29
RC-2026-06 | 2026-05 | FR-SA-01…03 | New listen-only mode that never replies | CR-2026-07 | Client C | Implemented 2026-05-11 → 08-16
RC-2026-07 | 2026-06 | FR-DS-01…04 | New document studio with and without templates | CR-2026-09 | Client D | Implemented 2026-06-20 → 06-27

## Summary
Summary — live formulas
Module | Requirements | Delivered | Must-have
2025 appliance
Platform
Knowledge chat
Live transcription
Silent Assistant
Boardroom
Voice
Document Studio
Total