## Document control
EM26-22 — Product Roadmap (2025 → 2027)
AJACE Inc. · EchoMind Product · ISO 9001:2015 evidence · Controlled in docs/qms (git); uncontrolled when printed
Field | Entry
Document ID | EM26-22
Title | Product Roadmap (2025 → 2027)
Version | 1.1
Date | 2026-10-12
Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA
Area / project | EchoMind Product — EchoMind (2025 pilot appliance) and EchoMind Enterprise (2026, repository RW2523/echomind-enterprise)
Status | APPROVED — rev 1.1 2026-10-12 (AR-2026-004); rev 1.0 2026-10-12 (AR-2026-003)
Purpose | The EchoMind roadmap: the 2025 plan and what actually happened to each item, the 2026 increments as delivered (dated by commits), and the forward plan with owners and dates.
Sources | 2025 roadmap and SDLC plan (EchoMind_SDLC_Project_Plan_Roadmap_Editions.xlsx); git history; REG-03 risk treatments and EM26-17 actions (approved 2026-10-07); SOP-13/15; product vision.
Copy | PUBLIC COPY — clients shown as Client A–D; the controlled copy given to the auditor carries the names
Status key | Planned = owner and date approved 2026-10-07 (REG-03 / EM26-17). Scheduled = fixed in a procedure. Proposed = for the next management review.
Dating rule | Every date comes from a record: a 2025 minute or review document, a git commit, a register entry or a test run. Where a remembered month and the commit record differed, the commit date is used. Nothing is back-dated.
Sheet | What it holds
Timeline | Month-by-month view May 2025 → Jun 2027 (green delivered, blue planned, amber proposed)
2025 plan vs actual | Every 2025 roadmap item and its outcome
Delivered 2026 | The six 2026 versions v1.0.0 → v1.4.1, dated by commits
Forward plan | Q4 2026 → H1 2027: owner, date, status, source
Milestones | Key dates
Role | Name | Signature | Date
Prepared by — Lead Engineer | Richard Watson Stephen Amudha | Richard Watson Stephen Amudha | 2026-10-12
Reviewed by — EchoMind Project Lead | Alexander Peter | Alexander Peter | 2026-10-12
Quality assurance — QA / MR | Sheryl Nazareth | Sheryl Nazareth | 2026-10-12
Approved by — Managing Director | Anita Johan | Anita Johan | 2026-10-12
Approval record
Rev 1.1: docs/qms/records/approvals/2026-10-12_AR-2026-004_register_revision_approval.md; rev 1.0: …/2026-10-12_AR-2026-003_register_approval.md. Review and approval confirmed by each role holder; signatures are their typed names (SOP-01 §6).
Date | Version | Owner | Change
2026-10-11 | 1.0 | Richard Watson Stephen Amudha (Lead Engineer) | First issue
2026-10-12 | 1.0 | Anita Johan (Managing Director) | Approved — AR-2026-003
2026-10-12 | 1.1 | Richard Watson Stephen Amudha (Lead Engineer) | Versions v1.0.0–v1.4.1 added (v1.0.0–v1.3.0 retrospective baselines, REG-08 §2a); version reviews
2026-10-12 | 1.1 | Anita Johan (Managing Director) | Approved — AR-2026-004

## Timeline
Timeline — May 2025 → June 2027
Green = delivered (dates from records). Blue = planned with an approved owner and date. Amber = proposed.
Workstream | 25-05 | 25-06 | 25-07 | 25-08 | 25-09 | 25-10 | 25-11 | 25-12 | 26-01 | 26-02 | 26-03 | 26-04 | 26-05 | 26-06 | 26-07 | 26-08 | 26-09 | 26-10 | 26-11 | 26-12 | 27-01 | 27-02 | 27-03 | 27-04 | 27-05 | 27-06
2025 appliance — architecture and requirements | bar: 25-05 to 25-06
2025 appliance — prototype, QA sprint, SOW | bar: 25-07 to 25-08
2025 appliance — release, delivery, audits | bar: 25-09 to 25-10
Platform move to the DGX Spark | bar: 26-01 to 26-02
Financial knowledge base (DoD FMR) | bar: 26-03 to 26-07
Conversation: Unmute → PersonaPlex → own dual loop | bar: 26-02 to 26-04
Live transcription accuracy and speed | bar: 26-04 to 26-07
Silent Assistant | bar: 26-05 to 26-08
Boardroom | bar: 26-05 to 26-09
Document Studio | bar: 26-06
Security: login, roles, tenancy, export gateway | bar: 26-06
TensorRT-LLM in production | bar: 26-03 to 26-07
Evaluation harness and QASC 2026 paper | bar: 26-07 to 26-08
Voice redesign; v1.4.0; QMS | bar: 26-09
v1.4.1; ISO surveillance audit | bar: 26-10
Risk treatments (backup, licences, login default, retention) | bar: 26-10
Internal audits (clauses 4–10) | bar: 26-11 to 27-01
Quality: barge-in, abstention, isolation, reranker | bar: 26-11
Database move; second engineer | bar: 26-12
Management reviews (quarterly) | bar: 26-12 to 27-03
Edge tier; export workflow; customisation kit | bar: 27-01 to 27-06
Versions (v1.0.0–v1.3.0 retrospective baselines; v1.4.x releases) | 26-02: 1.0.0; 26-04: 1.1.0; 26-06: 1.2.0; 26-08: 1.3.0; 26-09: 1.4.0; 26-10: 1.4.1

## 2025 plan vs actual
2025 roadmap (June 2025 → July 2026) — plan against what happened
The plan predates the 2026 platform move; items were delivered, delivered later on the new platform, superseded or not pursued.
Planned for | 2025 roadmap item | Outcome | What happened | Evidence
Q2 2025 | Enterprise White — baseline secure deployment | Delivered | 2025 pilot appliance delivered Sep 2025 (offline, on-premises) | DR-2025-13
Q2 2025 | Developer White — SDK and test environment | Not pursued | Focus moved to the enterprise appliance | —
Q2 2025 | Personal White — productivity apps | Superseded | Personal-assistant features delivered in 2026 (wake word, listen-only, memory) | FR-VC-03
Q2 2025 | Security framework alignment with AJACE standards | Delivered (2026) | Login, roles, tenancy, export gateway 2026-06-27; QMS approved 2026-10-07 | FR-PL-02…04
Q3 2025 | Enterprise Silver — role-based access, performance tuning | Delivered (2026) | RBAC 2026-06-27; TensorRT-LLM NVFP4 2026-07-29 | FR-PL-02; RC-2026-05
Q3 2025 | Developer Silver — extended APIs, plug-in marketplace | Partial | REST and WebSocket APIs exist; no marketplace | CAPABILITIES.md
Q3 2025 | Personal Silver — smart assistant with offline mode | Delivered (2026) | Offline voice assistant 2026-04-08 → 09-21 | FR-VC-01
Q3 2025 | Hardware optimisation for the appliance | Delivered (2026) | Moved to the DGX Spark 2026-02 | RC-2026-01
Q4 2025 | Enterprise Black — compliance suite (GDPR, HIPAA) | Not achieved | No certification claimed; data-protection controls in place (offline, redaction, isolation) | NFR-D01…D03
Q4 2025 | Developer Black — cloud-to-edge pipeline | Not pursued | Replaced by the edge-tier concept (proposed 2027) | Forward plan
Q4 2025 | Personal Black — multi-device sync | Not pursued | — | —
Q4 2025 | Pilot programmes with partners | Delivered | 2025 university pilot (Sep 2025); 2026 client pilots with Clients A–D | DR-2025-13; CR-2026-02…09
Q1 2026 | White/Silver/Black editions rolled out | Superseded | Replaced by vertical packs (banking, health, law, meetings, retail) 2026-06-27 | FR-PL-05
Q1 2026 | Analytics dashboard (Enterprise) | Partial | Usage metering and activity log 2026-06-27 | FR-PL-03
Q2 2026 | Improvements from lessons-learnt logs | Delivered | 2025 log (20 lessons) and 2026 log (17 lessons) feed REG-04 and the roadmap | EM26-16
Q2 2026 | High availability and disaster recovery | Partial | Backup and restore 2026-09-22; off-host copy due 2026-10-13; no HA cluster | FR-PL-09; R-02
Q3 2026 | Refine the product vision with AJACE leadership | Delivered | Building-block platform, edge tier, offline → online export gateway | Forward plan
Q3 2026 | Green AI — energy-efficient models | Partial | NVFP4 quantised 30B model on one desk-side system 2026-07-29 | RC-2026-05

## Delivered 2026
Delivered in 2026 — versions v1.0.0 → v1.4.1
v1.0.0–v1.3.0: retrospective baselines on the last commit of each two-month increment (REG-08 §2a). v1.4.0, v1.4.1: releases with release records.
Version | Window | Delivered | Version date | Commit | Version reviews | Type
v1.0.0 | Jan–Feb 2026 | 2025 code ported to the DGX Spark; knowledge chat with citations; live transcription; Kyutai speech; voice with barge-in; wake word and listen-only | 2026-02-27 | 595b24b | CR-2026-01, CR-2026-02, CR-2026-03 | Retrospective baseline — tagged 2026-10-12
v1.1.0 | Mar–Apr 2026 | DoD FMR knowledge base (section and TOC retrieval); financial assistant; TensorRT-LLM integrated; own dual-loop voice; Nemotron speech; personas; offline preparation | 2026-04-29 | e5292f3 | CR-2026-04, CR-2026-05, CR-2026-06, CR-2026-07 | Retrospective baseline — tagged 2026-10-12
v1.2.0 | May–Jun 2026 | Silent Assistant; Boardroom; code-audit fixes; Document Studio; Parakeet final STT; login, roles, tenancy, export gateway; vertical packs; public reference instance | 2026-06-27 | 46bd774 | CR-2026-08, SR-2026-01, CR-2026-09 | Retrospective baseline — tagged 2026-10-12
v1.3.0 | Jul–Aug 2026 | TensorRT-LLM NVFP4 in production; golden evaluation; retrieval fixes; RAG ingestion overhaul; Silent Assistant v2; QASC 2026 results | 2026-08-16 | bc9aa33 | RV-2026-01, RV-2026-02 | Retrospective baseline — tagged 2026-10-12
v1.4.0 | Sep 2026 | Voice redesign (speculative replies, tool routing); release identification; backup and restore; QMS documentation | 2026-09-22 | eaa7b1a | RV-2026-03, RV-2026-04, RV-2026-05, RV-2026-06 | Release (FRM-03) — tagged on the day
v1.4.1 | Oct 2026 | Defect fixes from acceptance testing; CI; external login check; CPU fallback for speech and embeddings | 2026-10-06 | f1b8445 | RV-2026-07, RV-2026-08 | Release (FRM-03) — tagged on the day

## Forward plan
Forward plan — Q4 2026 → H1 2027
Quarter | Item | Owner | Target | Status | Source
Q4 2026 | Off-host nightly backup installed | Kishan Haravu Pradeep | 2026-10-13 | Planned | REG-03 R-02; A-17-07
Q4 2026 | Evaluation corpus restored; golden suite re-run | Richard Watson Stephen Amudha | 2026-10-13 | Planned | NC-2026-008; A-17-05
Q4 2026 | ISO 9001 surveillance audit | Anita Johan | 2026-10-14 | Scheduled | AUDIT_PACK
Q4 2026 | Model licences verified (incl. gated models, SDXL-Turbo) | Richard Watson Stephen Amudha | 2026-10-31 | Planned | REG-03 R-10; ticket #56
Q4 2026 | Login default and CORS origin for customer installs | Kishan Haravu Pradeep | 2026-10-31 | Planned | REG-03 R-04
Q4 2026 | Retention periods and encryption at rest decided | Kishan Haravu Pradeep | 2026-10-31 | Planned | REG-03 R-06, R-13; A-17-08
Q4 2026 | GPU-sharing policy for the host | Richard Watson Stephen Amudha | 2026-10-31 | Planned | REG-03 R-14
Q4 2026 | Health checks for frontend and tunnel | Richard Watson Stephen Amudha | 2026-10-31 | Planned | A-17-06
Q4 2026 | Hotspot configuration under version control | Alexander Peter | 2026-10-31 | Planned | EM26-19 AC-26
Q4 2026 | Internal audit — clauses 4–7 | Sheryl Nazareth | 2026-11 | Scheduled | SOP-13 §4
Q4 2026 | Barge-in stop time under 1.0 s | Richard Watson Stephen Amudha | 2026-11-30 | Planned | NFR-P07; A-17-03
Q4 2026 | Abstention accuracy ≥ 0.80 | Richard Watson Stephen Amudha | 2026-11-30 | Planned | NFR-Q04; A-17-04
Q4 2026 | Tenant isolation made structural | Richard Watson Stephen Amudha | 2026-11-30 | Planned | REG-03 R-05
Q4 2026 | Reranker model pre-cached for offline use | Richard Watson Stephen Amudha | 2026-11-30 | Planned | REG-03 R-11
Q4 2026 | Internal audit — clause 8 | Sheryl Nazareth | 2026-12 | Scheduled | SOP-13 §4
Q4 2026 | First quarterly management review | Anita Johan | 2026-12 | Proposed | SOP-15 §4 (input pack EM26-02d)
Q4 2026 | Database move SQLite → Postgres for concurrency | Richard Watson Stephen Amudha | 2026-12-31 | Planned | REG-03 R-12; runbook 46bd774
Q4 2026 | Second engineer able to run releases (bus factor) | Anita Johan | 2026-12-31 | Planned | REG-03 R-03
Q1 2027 | Internal audit — clauses 9–10 | Sheryl Nazareth | 2027-01 | Scheduled | SOP-13 §4
Q1 2027 | API acceptance tests in CI | Richard Watson Stephen Amudha | 2027-Q1 | Proposed | Lesson LL-2026-12
Q1 2027 | Management review (quarterly) | Anita Johan | 2027-03 | Proposed | SOP-15 §4
H1 2027 | Edge-device tier: offline devices that use the host's knowledge base | EchoMind team | 2027-H1 | Proposed | Product vision
H1 2027 | Offline → online export gateway extended to a full approval workflow | EchoMind team | 2027-H1 | Proposed | Product vision; FR-PL-04
H1 2027 | Building-block customisation kit for client-specific deployments | EchoMind team | 2027-H1 | Proposed | Product vision

## Milestones
Milestones
Date | Milestone | Reference | Status
2025-05-15 | 2025 architecture approved | DR-2025-01 | Done
2025-08-05 | 2025 SOW signed | DR-2025-09 | Done
2025-09-20 | 2025 appliance released and shipped | DR-2025-13 | Done
2025-09-24 | Internal audit (6 observations, closed by 2025-10-11) | DR-2025-14 | Done
2025-10-16 | ISO 9001 Stage 2 certification audit | DR-2025-15 | Done
2026-01 | Decision to move to the DGX Spark | CR-2026-01 | Done
2026-02-05 | 2025 code running on the DGX Spark | 4b90b36 | Done
2026-02-27 | v1.0.0 baseline (retrospective) | 595b24b | Done
2026-04-08 | Own dual-loop voice architecture | ddc0aa3 | Done
2026-04-29 | v1.1.0 baseline (retrospective) | e5292f3 | Done
2026-06-27 | v1.2.0 baseline (retrospective) | 46bd774 | Done
2026-08-16 | v1.3.0 baseline (retrospective) | bc9aa33 | Done
2026-06-27 | Security and vertical packs | c9bad3d…f75121b | Done
2026-07-29 | TensorRT-LLM NVFP4 in production; golden evaluation | 80375c6, 12f7219 | Done
2026-08-07 | QASC 2026 paper results frozen | cbc57d1 | Done
2026-09-22 | Release v1.4.0 | eaa7b1a | Done
2026-10-06 | Release v1.4.1 | f1b8445 | Done
2026-10-07 | QMS documents approved | AR-2026-001 | Done
2026-10-14 | ISO 9001 surveillance audit | AUDIT_PACK | Scheduled
2026-11 → 2027-01 | Internal audits | SOP-13 | Scheduled