# Completion Checklist — what is needed to finish the ISO 9001 system

| Field | Value |
| --- | --- |
| Document ID | (working checklist — not a controlled QMS document) |
| Revision | 1.0 |
| Basis | docs/qms/ at revision 1.0, assessed 2026-09-21; progress updated 2026-09-22 (D1, D2, D6 closed); re-verified against the running system 2026-10-06 — D2 applied 2026-10-06; D14 built but not installed on the reference host; D4 deployed but not yet a from-scratch release build; D5 done |
| Companion documents | ADOPTION_GUIDE.md (the six-step path) · ISO9001_Gap_Analysis.md (the findings) |

## How to read this

Six categories, in dependency order. A, B and C you can finish in a few days — they are information and decisions. D is engineering work. E cannot be shortened at all — it is elapsed time accumulating real records, and it is the binding constraint on certification.

There are 1,581 blank fields in the document set. That number is misleading and worth decomposing, because most of them are not "missing":

| Where | Count | Do they need filling now? |
| --- | --- | --- |
| Blank forms (FRM-01…FRM-12) | ~1,275 | No. These are templates. A field is filled when the form is used for a real event. |
| Approval blocks (36 documents × header) | ~144 | Yes — category A4 |
| Registers and core documents | ~162 | Yes — categories A, B, C |

The questions in categories A and B are laid out as a fillable form in INTAKE_FORM.md. Answer that one document and everything below in A and B is covered.

## A. Information only you have

Nothing in the repository can supply these. Roughly one hour of work.

| # | What | Where it goes | Notes |
| --- | --- | --- | --- |
| ~~A1~~ ✅ 2026-10-07 | Registered company name, registered address, principal place of business, company registration number | QM-01 §1 table | Also used in the scope statement |
| ~~A2~~ ✅ 2026-10-07 | The location from which the service is provided | QM-01 §4 scope statement (line 82) | ISO requires the scope to state where |
| ~~A3~~ ✅ 2026-10-07 | Who holds each role: Managing Director, Lead Engineer, Quality representative, Data custodian | QM-01 §6.1 | One person may hold all four — record the same name four times; the roles stay distinct in records |
| ~~A4~~ ✅ 2026-10-07 | Approver name + date on every document, and a signature on the policy | 36 header blocks; QP-01 §signature | Must be your own act. Do not pre-fill, do not back-date. This is the single action that turns the set into a system. |
| A5 | Personnel names for the competence matrix | REG-05 §2, §3 | Nine competence rows already listed; add the person and the evidence for each |

## B. Decisions only you can make

Nobody can make these for you; they define what you are agreeing to be held to. Half a day.

| # | Decision | Where | Guidance |
| --- | --- | --- | --- |
| B1 | Accept, change or reject each of the 7 quality objectives and their targets | QO-01 | Only agree to targets you will actually measure. A missed target you track is fine; a target nobody measures is a finding. |
| B2 | Confirm or change the 14 proposed risk ratings, and assign an owner and due date to each treatment | REG-03 | The ratings are one reading of the evidence, deliberately marked proposed. This is the highest-value two hours in the whole adoption. |
| B3 | Data retention periods per data class — uploaded documents, transcripts, boardroom audio, chat messages, activity_log | SOP-11 §7 | Currently there is no policy at all. Customers in regulated sectors will ask this in procurement. Decide it per class, in days. |
| B4 | Management review cadence — quarterly or annual | SOP-15 §4; QO-01 QO-7 | Quarterly is better for a system this young; annual is the ISO minimum |
| B5 | Internal audit approach — (a) contract an external auditor, (b) wait for a second competent person, or (c) interim self-assessment | SOP-13 §4 | Only (a) and (b) satisfy 9.2.2 c. Option (c) is available now but is explicitly non-conformant and must stay logged as an open nonconformity. |
| B6 | Change significance criteria — what requires a formal change request rather than just a commit | SOP-06 §5 | Draft criteria are proposed; confirm or narrow them |
| B7 | Whether AUTH_ENABLED=1 becomes the default for customer deployments | SOP-11 §5; risk R-04 | A product decision with a compliance consequence |
| B8 | Audit programme dates — which clauses are audited in which period | SOP-13 §7 schedule table | 26 blank period cells |

## C. External facts to obtain

Research and verification, not authorship. One to two days.

| # | What | Where | Why it matters |
| --- | --- | --- | --- |
| C1 | Licence terms for all 11 models — commercial use, attribution, redistribution | REG-02 §2 licence column | You sell commercially into regulated sectors. This is the most likely question from a customer's legal team, and the answer is currently unknown. |
| C2 | Nemotron gated-model terms specifically — does acceptance permit redistribution baked into a customer-delivered image? | REG-02 action A-2 | The model is compiled into images you ship. If the terms do not permit it, that is a live legal exposure, not a paperwork gap. |
| C3 | SDXL-Turbo commercial-use terms | REG-02 action A-3 | Stability AI licensing has commercial conditions worth checking explicitly |
| C4 | A licensed copy of ISO 9001:2015 itself | REG-02 §6 | The standard is copyrighted and cannot live in the repo. You and any auditor need access to the text. |
| C5 | Rationale for the MIT Ubuntu mirror substitution, or remove it | SOP-09; REG-02 I-06 | An undeclared third-party dependency in the build path |

## D. Engineering work

These are the gaps in ISO9001_Gap_Analysis.md. Ordered by consequence, not by audit severity.

### Do before the next customer deployment

| # | Work | Gap / risk | Effort |
| --- | --- | --- | --- |
| ~~D1~~ | ~~Backup and restore for echomind_data, with a restore actually tested~~ — DONE 2026-09-22. scripts/backup_data.sh / restore_data.sh; restore verified (integrity_check ok, 32 tables). Residual: it is manual and written to the same host — see D14. | G-03 / R-02 / QO-4 | done |
| ~~D2~~ | ~~Log rotation on all six services~~ — DONE 2026-09-22 (50 MB × 5). Applies on the next docker compose up -d; running containers keep the old config until recreated. Applied 2026-10-06 — all six containers recreated and verified. | G-11 / R-07 | done |
| ~~D14~~ | ~~Schedule the backup and send it off-host~~ — DONE 2026-09-22. install_backup_timer.sh (nightly systemd timer) + BACKUP_REMOTE off-host replication, tested. You must choose the destination and run the installer on each deployment. Verified 2026-10-06: not installed on the reference host, BACKUP_REMOTE unset; the only backup is the manual one of 2026-09-22. | G-22 / R-02 | built; install |
| D3 | Extend the auth middleware to WebSocket endpoints; decide the CORS default. The public reference instance relies on application auth alone (restored 2026-10-06 after being found off — REG-04 NC-2026-009) | G-06 / R-04 | 2–3 days |

### Do before a certification attempt

| # | Work | Gap / risk | Effort |
| --- | --- | --- | --- |
| D4 | Release identification — git tag, image tags, and a build identifier the running system can report. Mostly done: v1.4.0 tagged (2026-09-22); v1.4.1 released and deployed 2026-10-06 with tagged images (1.4.1) — front end built from source, backend/voice layered on existing images; every service reports 1.4.1 / f1b8445. Remaining: a from-scratch backend/voice build. | G-01 / R-09 / QO-3 | ½ day left |
| ~~D5~~ | ~~Re-run the golden evaluation against HEAD~~ — DONE 2026-09-22: 9/52, corpus absent (REG-04 NC-2026-008). Restoring the corpus is the follow-up | G-10 / QO-2 | done |
| ~~D6~~ | ~~Retain evaluation reports as records~~ — DONE 2026-09-22; 24 historical reports now tracked | G-12 | done |
| D7 | CI running the unit suites at minimum; wire in scripts/verify_offline_readiness.sh, which exists and is called by nothing | G-02 / R-08 | 1 day |
| D8 | LICENSE, NOTICE, and an SBOM for the three images | G-05 / R-10 | 2–3 days |
| ~~D9~~ | ~~Pin nemo_toolkit~~ — DONE 2026-09-22, pinned to 60ce9407 (the build verified in production). Risk R-01 residual 20 → 4. | R-01 | done |
| D10 | Implement the retention policy decided in B3, including activity_log pruning | G-04 / R-06 | 1–2 days |

### Worth doing, lower urgency

| # | Work | Gap |
| --- | --- | --- |
| D11 | Make namespace filtering structural so a new retrieval path cannot bypass it | R-05 — this class of defect has already occurred twice |
| D12 | Pre-download the cross-encoder reranker in the Dockerfile; log a WARNING when the fallback engages | R-11 — a silent quality degradation today |
| D13 | Pin ollama/ollama and cloudflare/cloudflared to digests | R-01 family |

## E. Records that must accumulate — the real constraint

This is what cannot be compressed, and it is why certification takes months rather than weeks. A certification body needs to see the system operating, and operating evidence is created by time passing, not by writing documents. Creating these retrospectively would be falsification.

| # | Record | Minimum for certification | Where it goes |
| --- | --- | --- | --- |
| E1 | Management review minutes | At least one; two or three is materially stronger | records/management-review/, using FRM-07 |
| E2 | Internal audit report covering every clause | One full cycle, by an impartial auditor | records/audits/, using FRM-06 |
| E3 | Nonconformities raised and closed with effectiveness verified | Several, showing the full cycle — this is where most young systems fail | REG-04 §B + records/capa/, using FRM-05 |
| E4 | Objectives measured at two or more points so a trend exists | At least two measurement rounds | QO-01 + SOP-12 |
| E5 | Release records | One per release made after adoption | REG-08 + records/releases/, using FRM-03 |
| E6 | Supplier evaluations | The critical providers, using FRM-04 | REG-02 |
| E7 | Requirements review + satisfaction review for any engagement | Per customer, using FRM-11 and FRM-12 | REG-06 |
| E8 | Corrective action on the audit findings from E2 | Closed, with effectiveness verified | REG-04 |

Realistic elapsed time: three to six months from adoption to a credible certification audit, assuming A–D are done in the first few weeks.

## F. If you pursue certification

| # | Step | Note |
| --- | --- | --- |
| F1 | Choose an accredited certification body | Accreditation matters — UKAS, ANAB or your national equivalent. An unaccredited certificate is worth little to a regulated buyer. |
| F2 | Stage 1 readiness review | A documentation review. Book it once A–D are done and E is underway. |
| F3 | Close stage 1 findings | Expect some |
| F4 | Stage 2 certification audit | The operating-evidence audit — this is where E is tested |
| F5 | Surveillance audits | Typically annual, over a three-year cycle |

Budget and timescales vary by body and scope; obtain quotes at F1 rather than assuming.

## Summary — the shortest honest answer

| Category | Work | Elapsed |
| --- | --- | --- |
| A — your information | ~1 hour | Day 1 |
| B — your decisions | ~half a day | Day 1–2 |
| C — licence verification | 1–2 days | Week 1 |
| D1–D3 — operational gaps | 3–5 days | Week 1–2 |
| D4–D10 — certification gaps | ~1 week | Week 2–4 |
| E — accumulating records | cannot be shortened | 3–6 months |
| F — certification | depends on the body | +1–2 months |

Nothing in A–D is blocked on anything external. The only genuine external dependency is B5/E2 — an impartial auditor — and the only genuine time constraint is E.