## Document control
EM26-19 — Deliverable Review Feedback and Action Log (2025 → 2026)
AJACE Inc. · EchoMind Product · ISO 9001:2015 evidence · Controlled in docs/qms (git); uncontrolled when printed
Field | Entry
Document ID | EM26-19
Title | Deliverable Review Feedback and Action Log (2025 → 2026)
Version | 1.1
Date | 2026-10-12
Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA
Area / project | EchoMind Product — EchoMind (2025 pilot appliance) and EchoMind Enterprise (2026, repository RW2523/echomind-enterprise)
Status | APPROVED — rev 1.1 2026-10-12 (AR-2026-004); rev 1.0 2026-10-12 (AR-2026-003)
Purpose | Every review of an EchoMind deliverable from May 2025 to October 2026 — by clients, the Project Lead, engineering and auditors — with its feedback, decision, the actions raised, their owners, due dates and closure evidence; and the two-monthly review cycle.
Sources | 2025: minutes MM-ECHO-2025-05/07/09; Deliverables, Scheduling and Acceptance Criteria Review records (DR-1.0, SCH-1.0, ACC-1.0); SOW; internal audit 2025-09-24; Stage 2 audit 2025-10-16. 2026: git history, REG-10, EM26-18, REG-04, test runs.
Copy | PUBLIC COPY — clients shown as Client A–D; the controlled copy given to the auditor carries the names
Dating rule | Every date comes from a record: a 2025 minute or review document, a git commit, a register entry or a test run. Where a remembered month and the commit record differed, the commit date is used. Nothing is back-dated.
Sheet | What it holds
Review cycle | Two-month periods May 2025 → Oct 2026: version, reviews held, actions (counts are live formulas)
Version reviews | Six versions v1.0.0 → v1.4.1 with the reviews held for each (live formulas)
Review log | All 33 reviews with feedback, decision, record and the version reviewed
Action log | All actions with owner, due date, status, closure date, evidence and version
Summary | Reviews and actions by year and by source (live formulas)
Role | Name | Signature | Date
Prepared by — Lead Engineer | Richard Watson Stephen Amudha | Richard Watson Stephen Amudha | 2026-10-12
Reviewed by — EchoMind Project Lead | Alexander Peter | Alexander Peter | 2026-10-12
Quality assurance — QA / MR | Sheryl Nazareth | Sheryl Nazareth | 2026-10-12
Approved by — Managing Director | Anita Johan | Anita Johan | 2026-10-12
Approval record
Rev 1.1: docs/qms/records/approvals/2026-10-12_AR-2026-004_register_revision_approval.md; rev 1.0: …/2026-10-12_AR-2026-003_register_approval.md. Review and approval confirmed by each role holder; signatures are their typed names (SOP-01 §6).
Date | Version | Owner | Change
2026-10-11 | 1.0 | Richard Watson Stephen Amudha (Lead Engineer) | First issue
2026-10-12 | 1.0 | Anita Johan (Managing Director) | Approved — AR-2026-003
2026-10-12 | 1.1 | Richard Watson Stephen Amudha (Lead Engineer) | Versions v1.0.0–v1.4.1 added (v1.0.0–v1.3.0 retrospective baselines, REG-08 §2a); version reviews
2026-10-12 | 1.1 | Anita Johan (Managing Director) | Approved — AR-2026-004

## Review cycle
Review cycle — every two months, May 2025 → October 2026
Counts are live formulas over the Review log and Action log sheets.
Period | Window | Product state / version | Commits on main | Reviews held | Reviews | Actions raised | Actions closed | Review status
P-2025-1 | May–Jun 2025 | 2025 appliance — architecture, requirements and prototype plan | n/a (2025 repositories) | DR-2025-01, DR-2025-02, DR-2025-03, DR-2025-04 |  |  |  | Held
P-2025-2 | Jul–Aug 2025 | 2025 appliance — prototype hardware, QA sprint, SOW signed | n/a (2025 repositories) | DR-2025-05, DR-2025-06, DR-2025-07, DR-2025-08, DR-2025-09, DR-2025-10 |  |  |  | Held
P-2025-3 | Sep–Oct 2025 | 2025 appliance — final release package delivered; internal audit; Stage 2 certification audit | n/a (2025 repositories) | DR-2025-11, DR-2025-12, DR-2025-13, DR-2025-14, DR-2025-15 |  |  |  | Held
P-2025-4 | Nov–Dec 2025 | No product release (2025 project closed; next platform under evaluation) | n/a (2025 repositories) | None — no deliverable in the period |  |  |  | No review needed — no deliverable
P-2026-1 | Jan–Feb 2026 | v1.0.0 — platform decision; 2025 code ported to the DGX Spark | 84 | CR-2026-01 |  |  |  | Held
P-2026-2 | Mar–Apr 2026 | v1.1.0 — DoD FMR knowledge base; conversation v1 → v2 → own dual loop; TensorRT-LLM; Nemotron speech; hotspot | 32 | CR-2026-02, CR-2026-03, CR-2026-04, CR-2026-05, CR-2026-06 |  |  |  | Held
P-2026-3 | May–Jun 2026 | v1.2.0 — Silent Assistant, Boardroom, Document Studio, login and roles, vertical packs, public reference instance | 44 | CR-2026-07, CR-2026-08, CR-2026-09, SR-2026-01 |  |  |  | Held
P-2026-4 | Jul–Aug 2026 | v1.3.0 — TensorRT-LLM NVFP4 in production, golden evaluation, RAG overhaul, QASC 2026 paper | 39 | RV-2026-01, RV-2026-02 |  |  |  | Held
P-2026-5 | Sep–Oct 2026 | v1.4.0 (2026-09-22) and v1.4.1 (2026-10-06) — released with release records; QMS approved | 43 | RV-2026-03, RV-2026-04, RV-2026-05, RV-2026-06, RV-2026-07, RV-2026-08 |  |  |  | Held

## Version reviews
Version reviews — v1.0.0 → v1.4.1 (2026)
v1.0.0–v1.3.0 are retrospective baselines tagged on 2026-10-12 on the last commit of each increment; v1.4.0 and v1.4.1 are releases with release records (REG-08). Counts are live formulas.
Version | Type | Date | Commit | Window | Scope (from the commits) | Version reviews | Reviews | Actions raised | Actions closed | Review status
v1.0.0 | Retrospective baseline | 2026-02-27 | 595b24b | Jan–Feb 2026 | 2025 code ported to the DGX Spark; knowledge chat with citations; live transcription; Kyutai speech; voice with barge-in; wake word and listen-only | CR-2026-01, CR-2026-02, CR-2026-03 |  |  |  | Held
v1.1.0 | Retrospective baseline | 2026-04-29 | e5292f3 | Mar–Apr 2026 | DoD FMR knowledge base (section and TOC retrieval); financial assistant; TensorRT-LLM integrated; own dual-loop voice; Nemotron speech; personas; offline preparation | CR-2026-04, CR-2026-05, CR-2026-06, CR-2026-07 |  |  |  | Held
v1.2.0 | Retrospective baseline | 2026-06-27 | 46bd774 | May–Jun 2026 | Silent Assistant; Boardroom; code-audit fixes; Document Studio; Parakeet final STT; login, roles, tenancy, export gateway; vertical packs; public reference instance | CR-2026-08, SR-2026-01, CR-2026-09 |  |  |  | Held
v1.3.0 | Retrospective baseline | 2026-08-16 | bc9aa33 | Jul–Aug 2026 | TensorRT-LLM NVFP4 in production; golden evaluation; retrieval fixes; RAG ingestion overhaul; Silent Assistant v2; QASC 2026 results | RV-2026-01, RV-2026-02 |  |  |  | Held
v1.4.0 | Release (FRM-03) | 2026-09-22 | eaa7b1a | Sep 2026 | Voice redesign (speculative replies, tool routing); release identification; backup and restore; QMS documentation | RV-2026-03, RV-2026-04, RV-2026-05, RV-2026-06 |  |  |  | Held
v1.4.1 | Release (FRM-03) | 2026-10-06 | f1b8445 | Oct 2026 | Defect fixes from acceptance testing; CI; external login check; CPU fallback for speech and embeddings | RV-2026-07, RV-2026-08 |  |  |  | Held

## Review log
Review log — 2025 → 2026
Every review is backed by a record (minute, review document, audit report, commit or test run).
Review ID | Date | Period | Product / version reviewed | Deliverable | Review type | Source | Reviewed by | Feedback / findings | Decision / outcome | Record / evidence | Actions | Closed | Open | Version
DR-2025-01 | 2025-05-15 | P-2025-1 | 2025 appliance (pre-release) | System architecture design | Design review | Internal | Alexander Peter (EchoMind Project Lead) | Architecture reviewed against the offline RAG need | Approved with minor corrections | Deliverables Review DR-1.0 — MM-2025-05-01, Jira EMD-03 |  |  |  | 2025 appliance
DR-2025-02 | 2025-05-18 | P-2025-1 | 2025 appliance (pre-release) | Architecture alignment workshop | Design review (meeting) | Internal | Alexander Peter (chair); Project Manager, Lead Architect, QA Lead | Diagrams validated; concern about GPU memory allocation; QA asked for early prototype testing | Draft accepted with minor updates; prototype fast-tracked for June | Minutes MM-ECHO-2025-05 |  |  |  | 2025 appliance
DR-2025-03 | 2025-05-22 | P-2025-1 | 2025 appliance (pre-release) | Requirement validation | Requirements review | Internal | AJACE PM / Quality team | Requirements validated | Approved | Acceptance Criteria Review ACC-1.0 — MM-2025-05-02, Jira REQ-2025-05 |  |  |  | 2025 appliance
DR-2025-04 | 2025-06-05 | P-2025-1 | 2025 appliance (pre-release) | Deployment sprint planning | Schedule review | Internal | AJACE PM team | Deployment sprint scope and dates | Scheduled | Scheduling Review SCH-1.0 — MM-2025-06-01, Jira Sprint-2025-06 |  |  |  | 2025 appliance
DR-2025-05 | 2025-07-10 | P-2025-2 | 2025 appliance (prototype) | Prototype hardware | Deliverable review | Internal | Alexander Peter (EchoMind Project Lead) | Prototype hardware against the specification | Approved | Deliverables Review DR-1.0 — MM-2025-07-01, DocuSign SOW-2025-07 |  |  |  | 2025 appliance
DR-2025-06 | 2025-07-12 | P-2025-2 | 2025 appliance (prototype) | QA sprint planning | Test planning review (meeting) | Internal | Alexander Peter (chair); QA Manager, Project Manager, Dev Lead | QA backlog prioritised; transcription tests scheduled; defect triage twice a week | QA sprint plan approved; defect triage from 2025-07-15 | Minutes MM-ECHO-2025-07; SCH-1.0 MM-2025-07-02 |  |  |  | 2025 appliance
DR-2025-07 | 2025-07-15 | P-2025-2 | 2025 appliance (prototype) | Acceptance criteria mapping | Acceptance criteria review | Internal | AJACE Quality / UAT team | Acceptance criteria mapped to test cases | Completed | ACC-1.0 — MM-2025-07-03, test case TC-07 |  |  |  | 2025 appliance
DR-2025-08 | 2025-08-03 | P-2025-2 | 2025 appliance (prototype) | Technical documentation (draft v0.9) | Document review | Internal | Alexander Peter (Project Lead); Antony Johan (Project Sponsor) | Draft technical documentation reviewed | Review logged; outcome not stated in the record | ‘Deliverables formally logged and analysed’ record |  |  |  | 2025 appliance
DR-2025-09 | 2025-08-05 | P-2025-2 | 2025 appliance | Statement of work (requirements) | Requirements review with the customer | Client | 2025 university pilot customer procurement office; AJACE | Requirements: fully offline on-premises AI system; Pilot Program BYOA (application and consulting, onsite setup) | SOW signed by both parties | DocuSign envelope (ID in the controlled copy); ECH-QMS-010 |  |  |  | 2025 appliance
DR-2025-10 | 2025-08-25 | P-2025-2 | 2025 appliance | Final delivery milestones | Schedule review | Internal | AJACE PM team | Contract milestones checked | Validated | SCH-1.0 — MM-2025-08-01, contract milestone sheet |  |  |  | 2025 appliance
DR-2025-11 | 2025-09-05 | P-2025-3 | 2025 appliance | Design against SOW | Design verification review | Internal | AJACE Quality / UAT team | Design checked against the SOW | Closed | ACC-1.0 — MM-2025-09-02, DocuSign SOW-2025-09 |  |  |  | 2025 appliance
DR-2025-12 | 2025-09-14 | P-2025-3 | 2025 appliance | Provider performance | Provider review (meeting) | Internal | Alexander Peter (chair); Procurement Lead, Project Manager, Operations Lead | July batch on time, August batch late; one hardware defect returned | Supplier satisfactory; extra QA checks at delivery | Minutes MM-ECHO-2025-09 |  |  |  | 2025 appliance
DR-2025-13 | 2025-09-20 | P-2025-3 | 2025 appliance | Final release package | Release review | Internal | Alexander Peter (EchoMind Project Lead) | Release package and shipment checked | Approved and released | DR-1.0 — MM-2025-09-01, UPS tracking |  |  |  | 2025 appliance
DR-2025-14 | 2025-09-24 | P-2025-3 | 2025 appliance | EchoMind area — internal audit | Internal audit | Internal audit | Auditor VMK; auditee Alexander Peter | 6 observations: deliverable reviews not logged; no detailed schedule; acceptance criteria not documented; no provider review record; failed tests not documented; lessons not logged | Corrective actions implemented 2025-10-08 → 10-11 and verified | AFR (internal) rows 11–16 |  |  |  | 2025 appliance
DR-2025-15 | 2025-10-16 | P-2025-3 | 2025 appliance | AJACE Inc. — ISO 9001:2015 Stage 2 certification audit (EchoMind area) | External audit | External audit | Auditor VMK; auditee Alexander Peter | #6 (8.2.2, Minor NC) NFRs not recorded or monitored; #7 (9.1.1, Obs) no actions from review feedback; #10 (9.3.2, Minor NC) EchoMind hardware delay not in management review minutes | #6 and #7 closed 2026-10-07 (EM26-17, EM26-18); #10 is a senior-management finding | AFR Stage 2 — EchoMind |  |  |  | 2025 appliance
CR-2026-01 | 2026-01 | P-2026-1 | Planning for v1.0.0 (2025 appliance as baseline) | Platform for the next product generation | Management / engineering review of the 2025 appliance against new hardware | Internal | EchoMind team | A single-PC appliance limits capacity and portability; a portable AI supercomputer is now available | Move to a portable AI supercomputer (DGX Spark) | Decision recorded here; 4b90b36 |  |  |  | v1.0.0
CR-2026-02 | 2026-03 | P-2026-2 | v1.0.0 | Requirements — Client A; Client B (Bahrain) | Requirements review with the clients | Client | EchoMind team with the clients | 3 requirements: personal AI assistant; conversation assistance; DoD FMR financial knowledge base | Requirements accepted; three workstreams opened | 95d3512, 18715c7 |  |  |  | v1.0.0
CR-2026-03 | 2026-03 | P-2026-2 | v1.0.0 (conversation v1) | Conversation assistance v1 (Kyutai Unmute stack) | Client demonstration review | Client | Clients A and B | Not natural; too slow | Replace the Unmute stack (try PersonaPlex) | 4b90b36, bff6cf2 |  |  |  | v1.0.0
CR-2026-04 | 2026-03 | P-2026-2 | v1.1.0 in development (conversation v2) | Conversation assistance v2 (NVIDIA PersonaPlex) | Client demonstration review | Client | Clients A and B | Fast, but cannot use the customer's large knowledge base in spoken conversation | Build our own dual-loop architecture | ddc0aa3; QASC 2026 paper |  |  |  | v1.1.0
CR-2026-05 | 2026-04 | P-2026-2 | v1.1.0 in development | Field deployment of the unit | Design review | Internal | Alexander Peter (EchoMind Project Lead) | No way to reach a deployed unit on a site without a network | Build the boot-time hotspot | Deployment unit; 0818cdc |  |  |  | v1.1.0
CR-2026-06 | 2026-04 | P-2026-2 | v1.1.0 in development | Live transcription | Client feedback review | Client | Client A | Accuracy and speed below need (e.g. 'DoD FMR' heard as 'DODFMA') | Better speech model with fallback; move chat to TensorRT-LLM | d89aeda, b6a70d8, 80375c6 |  |  |  | v1.1.0
CR-2026-07 | 2026-05 | P-2026-3 | v1.1.0 (demonstrated) | Conversation and live transcript demonstration | Client review | Client | Client C (law firm) | Needs a listen-only assistant that pulls supporting data onto the screen while people speak | Build the Silent Assistant | ec9b180, f75121b, 7f2658a |  |  |  | v1.1.0
CR-2026-08 | 2026-05 | P-2026-3 | v1.2.0 in development | Group discussions (Boardroom) | Design review and model trials | Internal | EchoMind team | Speaker separation (diarisation) needed; model chosen by trial | Build Boardroom with diarisation | f540976, cf463aa, e1a337b |  |  |  | v1.2.0
CR-2026-09 | 2026-06 | P-2026-3 | v1.2.0 in development | Document creation | Client requirement review | Client | Client D (Gulf region) | PPT and PDF made locally, with and without a template, with images | Build Document Studio | 2d23f40, 66356f9 |  |  |  | v1.2.0
SR-2026-01 | 2026-06-18 | P-2026-3 | v1.2.0 in development | Security and defect review across RAG, transcription, Boardroom and voice | Code audit | Internal | Richard Watson Stephen Amudha | Path-traversal write in Boardroom uploads; markup injection in PDF export; prompt-injection exposure in chat, Boardroom and voice; full prompts logged at INFO; transcript session collisions | All fixed in the same change | b08cf25 |  |  |  | v1.2.0
RV-2026-01 | 2026-07-29 | P-2026-4 | v1.3.0 in development | Retrieval pipeline | Golden-question evaluation (52 questions) against the live stack | Internal | Richard Watson Stephen Amudha | 5 defects + 1 isolation regression | Fix the defects; keep the suite as a release gate | ebd232f, 4e27109 — REG-10 RF-2026-003 |  |  |  | v1.3.0
RV-2026-02 | 2026-08-07 | P-2026-4 | v1.3.0 in development | Research paper experiment campaign (E1–E10) | Measurements checked against the paper's own claims | Internal | Richard Watson Stephen Amudha | 4 substantive (2 contradict published claims) | Record contradicting results verbatim; correct claims | eval/paper/results/SUMMARY.json — RF-2026-002 |  |  |  | v1.3.0
RV-2026-03 | 2026-09-21 | P-2026-5 | v1.4.0 candidate | Voice change set (speculative reply, tool routing, GPU STT) | Structured adversarial review, five lenses, each finding independently verified | Internal | Richard Watson Stephen Amudha (AI-assisted, independent verification) | 40 raised; 22 confirmed; 18 refuted | Fix the 22 confirmed findings before release; record 18 refuted | ff29843 — RF-2026-001 |  |  |  | v1.4.0
RV-2026-04 | 2026-09-22 | P-2026-5 | v1.4.0 | Golden evaluation re-run for audit evidence | Measurement review | Internal | Richard Watson Stephen Amudha | Corpus absent (9/52) | Pre-flight check; restore the corpus | NC-2026-008; eval_20260922-135322.json |  |  |  | v1.4.0
RV-2026-05 | 2026-09-28 | P-2026-5 | v1.4.0 | Repository health check | Unit suites + type-check against HEAD | Internal | Richard Watson Stephen Amudha | 5 failing tests, 20 type errors | Fix tests; add CI | 5ddf8a6, 736ea61 — NC-2026-010 |  |  |  | v1.4.0
RV-2026-06 | 2026-10-06 | P-2026-5 | v1.4.0 (deployed) | October audit pack | Every claim re-verified against the running system | Internal | Richard Watson Stephen Amudha | 6 statements wrong (incl. no login on the public site) | Correct the pack; restore login | 855bd80, 1d7f154 — NC-2026-009 |  |  |  | v1.4.0
RV-2026-07 | 2026-10-06 | P-2026-5 | v1.4.1 candidate | Release candidate (13 acceptance test cases) | Executed acceptance tests, 4 runs | Internal | Richard Watson Stephen Amudha | 4 defects; re-tests found 2 more | Fix, re-test (4 runs), release v1.4.1 | e0ed4d0, 3feb5db, f1b8445 — NC-2026-012…016 |  |  |  | v1.4.1
RV-2026-08 | 2026-10-07 | P-2026-5 | v1.4.1 (public instance) | Public instance access logs | Log review for the ungated period | Internal | Richard Watson Stephen Amudha | Ungated 68 days; 64 scanner probes; no data change outside engineering work | External login check; record runtime changes | records/capa/2026-10-07_NC-2026-009_access_log_review.md |  |  |  | v1.4.1

## Action log
Action log — 2025 → 2026
‘Not evidenced’ = recorded as open in a 2025 minute with no later closure record. ‘Represents’ counts AC-04 as the 22 confirmed voice findings it stands for.
Action ID | From review | Period | Action | Owner | Status | Due | Closed on | Closure evidence | Ticket / link | Represents | Version
DA-2025-01 | DR-2025-02 | P-2025-1 | Update architecture diagrams with GPU allocation | Lead Architect | Not evidenced | 2025-05-25 |  | Recorded open in MM-ECHO-2025-05; no later closure record (superseded by the 2026 platform) |  | 1 | 2025 appliance
DA-2025-02 | DR-2025-02 | P-2025-1 | Prepare prototype test plan | QA Lead | Closed | 2025-06-05 | 2025-07-12 | QA sprint plan approved in MM-ECHO-2025-07 | DR-2025-06 | 1 | 2025 appliance
DA-2025-03 | DR-2025-06 | P-2025-2 | Finalise QA sprint board | QA Manager | Closed | 2025-07-14 | 2025-07-14 | Recorded closed in MM-ECHO-2025-07 |  | 1 | 2025 appliance
DA-2025-04 | DR-2025-06 | P-2025-2 | Confirm test environment set-up | Dev Lead | Not evidenced | 2025-07-16 |  | Recorded open in MM-ECHO-2025-07; regression run on 2025-09-05 used the test environment |  | 1 | 2025 appliance
DA-2025-05 | DR-2025-12 | P-2025-3 | Issue supplier performance scorecard | Procurement Lead | Closed | 2025-09-20 | 2025-10-10 | Provider scorecard Q3-2025 reviewed 2025-10-10 (AFR row 14); lessons log #6, CR-2025-03 |  | 1 | 2025 appliance
DA-2025-06 | DR-2025-12 | P-2025-3 | Document the new QA delivery check process | Operations Lead | Closed | 2025-09-25 | 2025-10 | Pre-acceptance QA checklist for vendors (lessons log #17, CR-2025-03) |  | 1 | 2025 appliance
DA-2025-07 | DR-2025-01 | P-2025-1 | Cross-check hardware specification against project needs before approval | Alexander Peter | Closed | 2025-05-15 | 2025-05-15 | Deliverables Review DR-1.0, risks and actions |  | 1 | 2025 appliance
DA-2025-08 | DR-2025-09 | P-2025-2 | Validation session with stakeholders on SOW requirement mismatches | AJACE PM team | Closed | 2025-07 | 2025-07 | DR-1.0 risks and actions; SOW signed 2025-08-05 |  | 1 | 2025 appliance
DA-2025-09 | DR-2025-13 | P-2025-3 | Mandatory QA checklist before release sign-off | QA | Closed | 2025-09 | 2025-09 | DR-1.0 risks and actions |  | 1 | 2025 appliance
DA-2025-10 | DR-2025-10 | P-2025-2 | Weekly milestone checks; backlog grooming; milestones tracked in Jira | AJACE PM team | Closed | 2025-09 | 2025-10-10 | SCH-1.0 risks and actions; AFR row 12 verified 2025-10-10 |  | 1 | 2025 appliance
DA-2025-11 | DR-2025-07 | P-2025-2 | Standard acceptance-criteria template; joint requirement reviews; SOW sign-off session | AJACE Quality / UAT team | Closed | 2025-09 | 2025-10-10 | ACC-1.0 risks and actions; AFR row 13 verified in sprint review 2025-10-10 |  | 1 | 2025 appliance
DA-2025-12 | DR-2025-14 | P-2025-3 | Deliverables review record with formal logging and reviewer sign-off | AJACE Quality team | Closed | 2025-10-08 | 2025-10-08 | AFR row 11 — verified by QA 2025-10-08 |  | 1 | 2025 appliance
DA-2025-13 | DR-2025-14 | P-2025-3 | Test failure → defect → regression documentation (DEF-2025-01, REG-2025-01) | QA | Closed | 2025-10-10 | 2025-10-10 | AFR row 15 — regression run 2025-09-05 confirmed QA-FAIL-01 resolved |  | 1 | 2025 appliance
DA-2025-14 | DR-2025-14 | P-2025-3 | Lessons-learnt logbook adopted | PMO | Closed | 2025-10-11 | 2025-10-11 | AFR row 16 — reviewed in internal audit 2025-10-11 |  | 1 | 2025 appliance
DA-2025-15 | DR-2025-15 | P-2025-3 | Record and monitor non-functional requirements (finding #6) | Richard Watson Stephen Amudha | Closed | 2026-10-07 | 2026-10-07 | REG-09; EM26-17 (targets approved AR-2026-001) | #49 | 1 | 2025 appliance
DA-2025-16 | DR-2025-15 | P-2025-3 | Log actions from review feedback of deliverables (finding #7) | Richard Watson Stephen Amudha | Closed | 2026-10-07 | 2026-10-07 | REG-10; EM26-18 |  | 1 | 2025 appliance
AC-20 | CR-2026-01 | P-2026-1 | Buy the first DGX Spark and port the 2025 code to it (ARM64) | EchoMind team | Closed | 2026-02 | 2026-02 | 4b90b36, c751d79 (2026-02-05) — 2025 code running on the DGX Spark | — | 1 | v1.0.0
AC-21 | CR-2026-02 | P-2026-2 | Personal AI assistant: financial-assistant behaviour, conversation memory, personas | Richard Watson Stephen Amudha | Closed | 2026-04 | 2026-04 | 95d3512, e59fd55 (2026-03-08); 518fb8e (2026-04-08); c6b834d (2026-06-27) | — | 1 | v1.0.0
AC-22 | CR-2026-02 | P-2026-2 | DoD FMR knowledge base: try BookRAG and PageIndex; adopt hierarchical section → chunk retrieval with table-of-contents routing and regulation-tuned query classification | Richard Watson Stephen Amudha | Closed | 2026-03 | 2026-03 | 31f1205, 045b1b1 (03-03); 18715c7, cfe3360 (03-05); 5057a30 (03-06). BookRAG 23ac2f9 (03-07) measured 43/52 vs 50/52 and was switched off (2decb99, 07-30); PageIndex evaluated, not adopted | — | 1 | v1.0.0
AC-23 | CR-2026-03 | P-2026-2 | Replace the Unmute stack with NVIDIA PersonaPlex | Richard Watson Stephen Amudha | Closed | 2026-03 | 2026-03 | Trial compared in the QASC 2026 paper; trial code not kept | — | 1 | v1.0.0
AC-24 | CR-2026-04 | P-2026-2 | Build our own dual-loop conversation architecture grounded in the customer's knowledge base | Richard Watson Stephen Amudha | Closed | 2026-04 | 2026-04 | ddc0aa3, d89aeda (04-08); fbbadd0 (05-28); 5ce8bbe, cbc57d1 (08-07) — 636 ms median first audio vs 866 ms single loop | — | 1 | v1.1.0
AC-25 | CR-2026-05 | P-2026-2 | Hotspot: unit raises a Wi-Fi hotspot at every boot and serves a landing page that opens the applications | Alexander Peter | Closed | 2026-04 | 2026-04 | Built on the deployment unit; offline preparation 0818cdc (2026-04-10) | — | 1 | v1.1.0
AC-26 | CR-2026-05 | P-2026-2 | Bring the hotspot configuration under version control and add it to the deployment guide | Alexander Peter | Open | 2026-10-31 |  | — | — | 1 | v1.1.0
AC-27 | CR-2026-06 | P-2026-2 | Replace Whisper with Nemotron streaming speech recognition for live transcription | Richard Watson Stephen Amudha | Closed | 2026-04-08 | 2026-04-08 | d89aeda, 172b94c, ddc0aa3 | — | 1 | v1.1.0
AC-28 | CR-2026-06 | P-2026-2 | Accurate final transcript with Parakeet-TDT and automatic fallback to the streaming model | Richard Watson Stephen Amudha | Closed | 2026-06-26 | 2026-06-26 | b6a70d8, 3a6b1f9 — fixes 'DoD FMR' → 'DODFMA' | — | 1 | v1.1.0
AC-29 | CR-2026-06 | P-2026-2 | Move chat generation from Ollama to TensorRT-LLM for speed | Richard Watson Stephen Amudha | Closed | 2026-07-29 | 2026-07-29 | 06e788a (03-20) integration; 80375c6 (07-29) Qwen3-30B-A3B NVFP4 on TensorRT-LLM; Ollama kept for embeddings and rollback | — | 1 | v1.1.0
AC-30 | CR-2026-07 | P-2026-3 | Silent Assistant: runs with the live transcript; an assistant and an agent check the content continuously and surface data and pointers on screen without replying | Richard Watson Stephen Amudha | Closed | 2026-05-11 | 2026-05-11 | ec9b180 (2026-05-11) | — | 1 | v1.1.0
AC-31 | CR-2026-07 | P-2026-3 | Law rule pack, always-surface mode, namespace awareness; sentence-level checks with quoted proof | Richard Watson Stephen Amudha | Closed | 2026-08-16 | 2026-08-16 | f75121b (06-27), 7f2658a (08-16) | — | 1 | v1.1.0
AC-32 | CR-2026-08 | P-2026-3 | Select a diarisation model by trial; build Boardroom (group discussion, speaker-separated transcript, report) | Richard Watson Stephen Amudha | Closed | 2026-05-27 | 2026-05-27 | f540976 (05-14), cf463aa (05-19), e1a337b (05-27); VibeVoice-ASR adopted (REG-02 M-06) | — | 1 | v1.2.0
AC-33 | CR-2026-08 | P-2026-3 | Harden Boardroom: report salvage when the model output is truncated | Richard Watson Stephen Amudha | Closed | 2026-09-04 | 2026-09-04 | b08cf25 (06-18), 724fb98 (09-04) | — | 1 | v1.2.0
AC-34 | CR-2026-09 | P-2026-3 | Evaluate image-generation and document models; build Document Studio with PDF and PPTX export, on-device images, with and without a template | Richard Watson Stephen Amudha | Closed | 2026-06-27 | 2026-06-27 | 2d23f40 (06-20), 66356f9 (06-27); SDXL-Turbo on device (REG-02) | — | 1 | v1.2.0
AC-35 | SR-2026-01 | P-2026-3 | Allow-list audio formats and contain upload paths (Boardroom) | Richard Watson Stephen Amudha | Closed | 2026-06-18 | 2026-06-18 | b08cf25 | — | 1 | v1.2.0
AC-36 | SR-2026-01 | P-2026-3 | Escape all LLM and transcript text in PDF export | Richard Watson Stephen Amudha | Closed | 2026-06-18 | 2026-06-18 | b08cf25 | — | 1 | v1.2.0
AC-37 | SR-2026-01 | P-2026-3 | Prompt-injection guards and fenced untrusted context in chat, Boardroom and voice | Richard Watson Stephen Amudha | Closed | 2026-06-18 | 2026-06-18 | b08cf25; unit tests run by CI since 2026-10-07 | — | 1 | v1.2.0
AC-38 | SR-2026-01 | P-2026-3 | Stop logging full prompts at INFO; server-generated transcript session IDs | Richard Watson Stephen Amudha | Closed | 2026-06-18 | 2026-06-18 | b08cf25 | — | 1 | v1.2.0
AC-01 | RV-2026-01 | P-2026-4 | Enforce namespace predicate on the sparse transcript path; audit all paths | Richard Watson Stephen Amudha | Closed | 2026-08-07 | 2026-08-07 | 4e27109 — 0/359 out-of-namespace hits | — | 1 | v1.3.0
AC-02 | RV-2026-01 | P-2026-4 | Fix five retrieval defects found by the golden suite | Richard Watson Stephen Amudha | Closed | 2026-07-29 | 2026-07-29 | ebd232f — suite restored to 49/52 | — | 1 | v1.3.0
AC-03 | RV-2026-02 | P-2026-4 | Record contradicting findings verbatim; correct the claims in the next paper version | Richard Watson Stephen Amudha | Open (recording done) | Next version |  | SUMMARY.json | #19, #27 | 1 | v1.3.0
AC-04 | RV-2026-03 | P-2026-5 | 22 confirmed voice findings fixed before release (e.g. abort blocking the event loop; WebSocket close not aborting generation; hold phrase racing the answer; mid-word text split) | Richard Watson Stephen Amudha | Closed | 2026-09-21 | 2026-09-21 | ff29843 — 12/12 spoken turns, barge-in verified, 0 CUDA errors | — | 22 | v1.4.0
AC-05 | RV-2026-04 | P-2026-5 | Make the evaluation abort when its corpus is missing | Richard Watson Stephen Amudha | Closed | 2026-10-07 | 2026-10-07 | f3aca50 — aborts listing 15 documents | #48 | 1 | v1.4.0
AC-06 | RV-2026-04 | P-2026-5 | Restore the evaluation corpus and re-measure | Richard Watson Stephen Amudha | Open | 2026-10-13 |  | — | #47 | 1 | v1.4.0
AC-07 | RV-2026-05 | P-2026-5 | Correct stale tests and type errors | Richard Watson Stephen Amudha | Closed | 2026-09-28 | 2026-09-28 | 5ddf8a6, 736ea61 | — | 1 | v1.4.0
AC-08 | RV-2026-05 | P-2026-5 | Run the suites automatically on every push (CI) | Richard Watson Stephen Amudha | Closed | 2026-10-07 | 2026-10-07 | CI runs 37561379960 (pass) / 37561804619 (fails on broken test) | #50 | 1 | v1.4.0
AC-09 | RV-2026-06 | P-2026-5 | Restore application login on the public instance | Richard Watson Stephen Amudha | Closed | 2026-10-06 | 2026-10-06 | Externally verified 401 | #29 | 1 | v1.4.0
AC-10 | RV-2026-06 | P-2026-5 | Correct the audit pack and registers against the running system | Richard Watson Stephen Amudha | Closed | 2026-10-06 | 2026-10-06 | 855bd80, 1d7f154 | #40 | 1 | v1.4.0
AC-11 | RV-2026-07 | P-2026-5 | Logout revokes tokens; upload allow-list; small-talk routing; export key formats | Richard Watson Stephen Amudha | Closed | 2026-10-06 | 2026-10-06 | e0ed4d0 + 14 regression tests; run 4 pass | #32–#35 | 1 | v1.4.1
AC-12 | RV-2026-07 | P-2026-5 | Activity log identifies the caller before logout revokes the token | Richard Watson Stephen Amudha | Closed | 2026-10-06 | 2026-10-06 | 3feb5db; run 4 AC-101.8 pass | #32 | 1 | v1.4.1
AC-13 | RV-2026-07 | P-2026-5 | Embedding service on CPU; healthcheck makes a real embedding | Richard Watson Stephen Amudha | Closed | 2026-10-07 | 2026-10-07 | DC-2026-005; f3aca50 | #59 | 1 | v1.4.1
AC-14 | RV-2026-07 | P-2026-5 | Decide the GPU-sharing policy for the host | Anita Johan | Open | 2026-10-31 |  | — | #60 | 1 | v1.4.1
AC-15 | RV-2026-07 | P-2026-5 | Sign the v1.4.0 and v1.4.1 release records | Anita Johan | Open | 2026-10-13 |  | — | #61 | 1 | v1.4.1
AC-16 | RV-2026-08 | P-2026-5 | External login check every 6 hours | Richard Watson Stephen Amudha | Closed | 2026-10-07 | 2026-10-07 | run 37561803121 | #51 | 1 | v1.4.1
AC-17 | RV-2026-08 | P-2026-5 | Record runtime-setting changes (SOP-06 §10.1, drift check) | Richard Watson Stephen Amudha | Closed | 2026-10-07 | 2026-10-07 | f3aca50 | #52 | 1 | v1.4.1
AC-18 | RV-2026-08 | P-2026-5 | Confirm the 2026-08-07 / 08-16 / 09-15 knowledge-base operations were internal; check Cloudflare analytics | Kishan Haravu Pradeep | Open | 2026-10-13 |  | — | #53 follow-up | 1 | v1.4.1
AC-19 | RV-2026-08 | P-2026-5 | Record the real client address (CF-Connecting-IP) in the activity log; retain proxy logs | Richard Watson Stephen Amudha | Open | 2026-10-31 |  | — | — | 1 | v1.4.1

## Summary
Summary — live formulas
Group | Reviews | Actions raised | Actions closed
2025 reviews
2026 client and design reviews
2026 code audit
2026 engineering and quality reviews
Total
Review source | Reviews
Client
Internal
Internal audit
External audit