AJACE INC.  ·  ECHOMIND ENTERPRISE  ·  ISO 9001:2015 EVIDENCE

# Project Plan — EchoMind Enterprise

# Document control

| Field | Value |
| --- | --- |
| Document ID | EM26-23 |
| Title | Project Plan — EchoMind Enterprise |
| Version | 1.0 |
| Issue date | 2026-10-13 |
| Status | APPROVED — 2026-10-13 (AR-2026-005) |
| Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA |
| Project | EchoMind Product (Project 2) |
| Prepared by | Richard Watson Stephen Amudha (Lead Engineer) — 2026-10-13 |
| Reviewed by | Alexander Peter (EchoMind Project Lead) — 2026-10-13 |
| Quality assurance | Sheryl Nazareth (QA / MR) — 2026-10-13 |
| Approved by | Anita Johan (Managing Director) — 2026-10-13 |

# 1. Purpose and scope

This plan describes how the EchoMind Enterprise project is organised, delivered and controlled: the scope, the organisation, the delivery cycle and versions, how the client is kept involved, how quality and risk are managed, and the plan ahead. It follows the 2025 university pilot appliance, delivered in September 2025.

| Item | Entry |
| --- | --- |
| Product | EchoMind Enterprise — an on-premises AI workspace: knowledge chat with citations, live transcription with the Silent Assistant, Boardroom, voice conversation and Document Studio |
| Platform | NVIDIA DGX Spark (Grace-Blackwell GB10), fully offline |
| Clients | Client A; Client B (Bahrain); Client C (law firm); Client D (Gulf region) |
| Repository | github.com/RW2523/echomind-enterprise (versions tagged v1.0.0 → v1.4.1) |

# 2. Organisation and responsibilities

| Role | Name | Responsibility in the project |
| --- | --- | --- |
| Managing Director | Anita Johan | Approves the plan, releases and documents; owns resources |
| EchoMind Project Lead | Alexander Peter | Client relationship and reviews; design reviews; deployment approach |
| Lead Engineer | Richard Watson Stephen Amudha | Design, development, verification, releases |
| QA / Management Representative | Sheryl Nazareth | QMS, records, audit programme |
| Data custodian | Kishan Haravu Pradeep | Customer data, backups, retention, access |

# 3. Delivery cycle and versions

Work is delivered in increments of about two months. Each increment ends with a version and is reviewed — with the clients for new capabilities, and by engineering for quality and release readiness.

| Version | Date | Window | Scope | Version reviews | Type |
| --- | --- | --- | --- | --- | --- |
| v1.0.0 | 2026-02-27 | Jan–Feb 2026 | 2025 code ported to the DGX Spark; knowledge chat with citations; live transcription; Kyutai speech; voice with barge-in; wake word and listen-only | CR-2026-01, CR-2026-02, CR-2026-03 | Retrospective baseline |
| v1.1.0 | 2026-04-29 | Mar–Apr 2026 | DoD FMR knowledge base (section and TOC retrieval); financial assistant; TensorRT-LLM integrated; own dual-loop voice; Nemotron speech; personas; offline preparation | CR-2026-04, CR-2026-05, CR-2026-06, CR-2026-07 | Retrospective baseline |
| v1.2.0 | 2026-06-27 | May–Jun 2026 | Silent Assistant; Boardroom; code-audit fixes; Document Studio; Parakeet final STT; login, roles, tenancy, export gateway; vertical packs; public reference instance | CR-2026-08, SR-2026-01, CR-2026-09 | Retrospective baseline |
| v1.3.0 | 2026-08-16 | Jul–Aug 2026 | TensorRT-LLM NVFP4 in production; golden evaluation; retrieval fixes; RAG ingestion overhaul; Silent Assistant v2; QASC 2026 results | RV-2026-01, RV-2026-02 | Retrospective baseline |
| v1.4.0 | 2026-09-22 | Sep 2026 | Voice redesign (speculative replies, tool routing); release identification; backup and restore; QMS documentation | RV-2026-03, RV-2026-04, RV-2026-05, RV-2026-06 | Release (FRM-03) |
| v1.4.1 | 2026-10-06 | Oct 2026 | Defect fixes from acceptance testing; CI; external login check; CPU fallback for speech and embeddings | RV-2026-07, RV-2026-08 | Release (FRM-03) |

# 4. Client involvement and communication

- Each new capability is shown to the client who asked for it; the feedback is recorded as a client review (CR-2026-xx) with its actions (EM26-19).

- Requirements and their changes are recorded in EM26-20 (functional) and EM26-21 (non-functional); each change names the review that decided it.

- Internal channels: GitHub project board, e-mail and Teams; client contact is held by the EchoMind Project Lead (SOP-04 §7).

# 5. Quality plan

| Control | How | When |
| --- | --- | --- |
| Reviews | Client, design and engineering reviews with actions (EM26-19) | Every increment (about two months) and before each release |
| Verification | Unit tests and type check in CI; 13 acceptance test cases; golden-question suite; research harness (EM26-24 Test Plan) | Every push; every release |
| Release | Release record FRM-03 authorised by the Managing Director; version tag; changelog | Every release |
| Nonconformities | REG-04 with correction, corrective action and re-test | When found |
| Requirements | FR and NFR registers with targets and measurements | Each release and management review |

# 6. Risks

Risks are kept in REG-03 with owners and due dates (14 risks). The main ones for the plan: shared GPU on the reference system (R-14), off-host backup (R-02), model licences (R-10), login default for customer installations (R-04).

# 7. Change control

Significant changes follow SOP-06 §6 (change request FRM-02, register REG-07). Requirement changes are recorded in EM26-20 › Requirement changes.

# 8. Plan ahead

| When | Item | Owner | Target | Status |
| --- | --- | --- | --- | --- |
| Q4 2026 | Off-host nightly backup installed | Kishan Haravu Pradeep | 2026-10-13 | Planned |
| Q4 2026 | Evaluation corpus restored; golden suite re-run | Richard Watson Stephen Amudha | 2026-10-13 | Planned |
| Q4 2026 | ISO 9001 surveillance audit | Anita Johan | 2026-10-14 | Scheduled |
| Q4 2026 | Model licences verified (incl. gated models, SDXL-Turbo) | Richard Watson Stephen Amudha | 2026-10-31 | Planned |
| Q4 2026 | Login default and CORS origin for customer installs | Kishan Haravu Pradeep | 2026-10-31 | Planned |
| Q4 2026 | Retention periods and encryption at rest decided | Kishan Haravu Pradeep | 2026-10-31 | Planned |
| Q4 2026 | GPU-sharing policy for the host | Richard Watson Stephen Amudha | 2026-10-31 | Planned |
| Q4 2026 | Health checks for frontend and tunnel | Richard Watson Stephen Amudha | 2026-10-31 | Planned |
| Q4 2026 | Hotspot configuration under version control | Alexander Peter | 2026-10-31 | Planned |
| Q4 2026 | Internal audit — clauses 4–7 | Sheryl Nazareth | 2026-11 | Scheduled |
| Q4 2026 | Barge-in stop time under 1.0 s | Richard Watson Stephen Amudha | 2026-11-30 | Planned |
| Q4 2026 | Abstention accuracy ≥ 0.80 | Richard Watson Stephen Amudha | 2026-11-30 | Planned |
| Q4 2026 | Tenant isolation made structural | Richard Watson Stephen Amudha | 2026-11-30 | Planned |
| Q4 2026 | Reranker model pre-cached for offline use | Richard Watson Stephen Amudha | 2026-11-30 | Planned |
| Q4 2026 | Internal audit — clause 8 | Sheryl Nazareth | 2026-12 | Scheduled |
| Q4 2026 | First quarterly management review | Anita Johan | 2026-12 | Proposed |
| Q4 2026 | Database move SQLite → Postgres for concurrency | Richard Watson Stephen Amudha | 2026-12-31 | Planned |
| Q4 2026 | Second engineer able to run releases (bus factor) | Anita Johan | 2026-12-31 | Planned |
| Q1 2027 | Internal audit — clauses 9–10 | Sheryl Nazareth | 2027-01 | Scheduled |
| Q1 2027 | API acceptance tests in CI | Richard Watson Stephen Amudha | 2027-Q1 | Proposed |
| Q1 2027 | Management review (quarterly) | Anita Johan | 2027-03 | Proposed |
| H1 2027 | Edge-device tier: offline devices that use the host's knowledge base | EchoMind team | 2027-H1 | Proposed |
| H1 2027 | Offline → online export gateway extended to a full approval workflow | EchoMind team | 2027-H1 | Proposed |
| H1 2027 | Building-block customisation kit for client-specific deployments | EchoMind team | 2027-H1 | Proposed |

# 9. Plan reviews held

The plan has been reviewed at each version review; the record of each review is in EM26-19.

| When | Reviews | What was reviewed | Effect on the plan |
| --- | --- | --- | --- |
| 2026-01 | CR-2026-01 | Platform decision: move from the 2025 PC appliance to the DGX Spark; first increment planned | Plan baselined for v1.0.0 |
| 2026-03 → 04 | CR-2026-02 … CR-2026-06 | Client requirements (personal assistant, conversation assistance, DoD FMR knowledge base); conversation approach changed twice; transcript accuracy and speed | Scope of v1.1.0 set; voice re-planned to the dual loop |
| 2026-05 → 06 | CR-2026-07 … CR-2026-09, SR-2026-01 | Law-firm Silent Assistant, Boardroom, Document Studio; security and defect review | Scope of v1.2.0 extended; security work brought forward |
| 2026-07 → 08 | RV-2026-01, RV-2026-02 | Golden-suite and research measurements | v1.3.0 focused on accuracy, isolation and measurement |
| 2026-09 → 10 | RV-2026-03 … RV-2026-08 | Voice review, release readiness, acceptance testing, audit readiness | Releases v1.4.0 and v1.4.1; forward plan to 2027 |