## Communication log
Communication log
EM26-27 Client communication log — issued 2026-10-13. Dates from the 2025 plan, Jira and SOW, and from the 2026 client reviews (EM26-19).
Date | Client | Direction | Subject / outcome | Channel | Record | Year
2025-05-29 | 2025 university pilot customer | AJACE → client | Product documentation, specification and sizing sent | E-mail | SDLC plan P1–P3 (‘done as per email’) | 2025
2025-06-03 | 2025 university pilot customer | AJACE → client | Contract revised (upfront-payment clause removed, reviewed with Antony Johan) and sent | E-mail (PDF) | SDLC plan C1–C3; signed contract held by AJACE | 2025
2025-07 | 2025 university pilot customer | AJACE → client | Follow-up on the purchase-order delay (client financial audit); August kick-off confirmed | E-mail | Jira EMD-02 | 2025
2025-08-05 | 2025 university pilot customer | Both | Statement of work signed by both parties | DocuSign | Project documentation; DR-2025-09 | 2025
2025-09 | 2025 university pilot customer | AJACE → client | Shipping confirmation and tracking; delivery ETA 2025-09-17 | E-mail | Jira EMD-12 | 2025
2025-09-20 | 2025 university pilot customer | AJACE | Final release package approved and released | Review | DR-1.0 (MM-2025-09-01) | 2025
2026-03 | Client A; Client B (Bahrain) | Client ↔ AJACE | Requirements — Client A; Client B (Bahrain): 3 requirements: personal AI assistant; conversation assistance; DoD FMR financial knowledge base | Demonstration / meeting | Review record CR-2026-02; correspondence to be filed | 2026
2026-03 | Client A; Client B (Bahrain) | Client ↔ AJACE | Conversation assistance v1 (Kyutai Unmute stack): Not natural; too slow | Demonstration / meeting | Review record CR-2026-03; correspondence to be filed | 2026
2026-03 | Client A; Client B (Bahrain) | Client ↔ AJACE | Conversation assistance v2 (NVIDIA PersonaPlex): Fast, but cannot use the customer's large knowledge base in spoken conversation | Demonstration / meeting | Review record CR-2026-04; correspondence to be filed | 2026
2026-04 | Client A | Client ↔ AJACE | Live transcription: Accuracy and speed below need (e.g. 'DoD FMR' heard as 'DODFMA') | Demonstration / meeting | Review record CR-2026-06; correspondence to be filed | 2026
2026-05 | Client C (law firm) | Client ↔ AJACE | Conversation and live transcript demonstration: Needs a listen-only assistant that pulls supporting data onto the screen while people speak | Demonstration / meeting | Review record CR-2026-07; correspondence to be filed | 2026
2026-06 | Client D (Gulf region) | Client ↔ AJACE | Document creation: PPT and PDF made locally, with and without a template, with images | Demonstration / meeting | Review record CR-2026-09; correspondence to be filed | 2026

## Document control
Document control
Document control
Field | Entry
Document ID | EM26-27
Title | Client Communication Log
Version | 1.0
Issue date | 2026-10-13
Status | APPROVED — 2026-10-13 (AR-2026-005)
Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA
Project | EchoMind Product (Project 2)
Prepared by | Richard Watson Stephen Amudha (Lead Engineer) — 2026-10-13
Reviewed by | Alexander Peter (EchoMind Project Lead) — 2026-10-13
Quality assurance | Sheryl Nazareth (QA / MR) — 2026-10-13
Approved by | Anita Johan (Managing Director) — 2026-10-13