## Document control
EM26-21 — Non-Functional Requirements Register (2025 → 2026)
AJACE Inc. · EchoMind Product · ISO 9001:2015 evidence · Controlled in docs/qms (git); uncontrolled when printed
Field | Entry
Document ID | EM26-21
Title | Non-Functional Requirements Register (2025 → 2026)
Version | 1.1
Date | 2026-10-12
Organisation | AJACE Inc. — 14159 Robert Paris Ct., Suite A, Chantilly, VA 20151, USA
Area / project | EchoMind Product — EchoMind (2025 pilot appliance) and EchoMind Enterprise (2026, repository RW2523/echomind-enterprise)
Status | APPROVED — rev 1.1 2026-10-12 (AR-2026-004); rev 1.0 2026-10-12 (AR-2026-003)
Purpose | The non-functional requirements (performance, accuracy, security, reliability, maintainability, data protection) — where each came from, its approved target, how and how often it is measured, every recorded measurement, and the status. Closes 2025 audit finding #6 (8.2.2).
Sources | REG-09 and EM26-17 (targets approved 2026-10-07, AR-2026-001); eval/reports (24 golden runs); eval/paper (E1–E10); acceptance runs 1–4; CI; 2025 SOW and lessons log.
Copy | PUBLIC COPY — clients shown as Client A–D; the controlled copy given to the auditor carries the names
Dating rule | Every date comes from a record: a 2025 minute or review document, a git commit, a register entry or a test run. Where a remembered month and the commit record differed, the commit date is used. Nothing is back-dated.
Sheet | What it holds
NFR register | 31 current NFRs: origin, target, latest measurement, status, monitoring frequency, owner
2025 NFRs | The 2025 appliance NFRs and where each was carried
Measurement history | Every recorded measurement, with date, version and source (golden suite, paper harness, acceptance runs, CI)
Monitoring plan | What is measured, how often and how
Summary | Status counts (live formulas)
Role | Name | Signature | Date
Prepared by — Lead Engineer | Richard Watson Stephen Amudha | Richard Watson Stephen Amudha | 2026-10-12
Reviewed by — EchoMind Project Lead | Alexander Peter | Alexander Peter | 2026-10-12
Quality assurance — QA / MR | Sheryl Nazareth | Sheryl Nazareth | 2026-10-12
Approved by — Managing Director | Anita Johan | Anita Johan | 2026-10-12
Approval record
Rev 1.1: docs/qms/records/approvals/2026-10-12_AR-2026-004_register_revision_approval.md; rev 1.0: …/2026-10-12_AR-2026-003_register_approval.md. Review and approval confirmed by each role holder; signatures are their typed names (SOP-01 §6).
Date | Version | Owner | Change
2026-10-11 | 1.0 | Richard Watson Stephen Amudha (Lead Engineer) | First issue
2026-10-12 | 1.0 | Anita Johan (Managing Director) | Approved — AR-2026-003
2026-10-12 | 1.1 | Richard Watson Stephen Amudha (Lead Engineer) | Versions v1.0.0–v1.4.1 added (v1.0.0–v1.3.0 retrospective baselines, REG-08 §2a); version reviews
2026-10-12 | 1.1 | Anita Johan (Managing Director) | Approved — AR-2026-004

## NFR register
Non-functional requirements — current register
Targets approved by the Managing Director on 2026-10-07 (AR-2026-001). First recorded in REG-09 on 2026-09-22.
NFR ID | Category | Requirement | Origin (review) | Raised | Why | Target | Target approved | Latest measured | Measured on | Status | Monitoring frequency | Method / evidence | Owner
NFR-P01 | Performance | Grounded chat answer latency | CR-2026-06 | 2026-04 | Client A: answers too slow | median ≤ 4 s; p95 ≤ 16 s | 2026-10-07 | median 3.31 s; p95 15.17 s (n=30) | 2026-08-07 | Meets | Per study / major change | Paper harness E1 — eval/paper/results/e1_latency.json | Richard Watson Stephen Amudha
NFR-P02 | Performance | Retrieval share of answer latency | RV-2026-02 | 2026-08-07 | Paper study | Monitor only (no target) | 2026-10-07 | 2.8 % | 2026-08-07 | Monitored | Per study / major change | E1 decomposition | Richard Watson Stephen Amudha
NFR-P03 | Performance | Tenant permission-filter overhead | RV-2026-02 | 2026-08-07 | Paper study | ≤ 1 ms | 2026-10-07 | 0.08 ms | 2026-08-07 | Meets | Per study / major change | E1 | Richard Watson Stephen Amudha
NFR-P04 | Performance | Voice: end of speech → first audible reply (dual-loop) | CR-2026-03 | 2026-03 | Clients A and B: conversation slow and not natural | median ≤ 1.0 s | 2026-10-07 | median 636 ms; p95 894 ms (n=10) | 2026-08-07 | Meets | Per study / major change | E10 ablation — e10_ablation.json; paper | Richard Watson Stephen Amudha
NFR-P05 | Performance | Voice first reply after speculative-reply work | RV-2026-03 | 2026-09-21 | Voice redesign review | median ≤ 1.0 s | 2026-10-07 | 0.14–0.49 s on GPU (12 turns, 2 personas); on CPU since 2026-10-06 — to re-measure | 2026-09-21 | Meets (GPU) — re-measure on CPU | Each release | voice_e2e session test; commit ff29843 | Richard Watson Stephen Amudha
NFR-P06 | Performance | Final speech-to-text decode time | CR-2026-06 | 2026-04 | Client A: transcript speed | ≤ 300 ms (GPU) / ≤ 1.6 s (CPU mode) | 2026-10-07 | 70–130 ms on GPU; CPU mode since 2026-10-06 — to re-measure | 2026-09-21 | Re-measure | Each release | commit ff29843 | Richard Watson Stephen Amudha
NFR-P07 | Performance | Barge-in: interrupt → assistant audio stops | CR-2026-03 | 2026-03 | Clients A and B: natural turn-taking | median ≤ 1.0 s | 2026-10-07 | median 2.13 s, success 1.00 (n=8) | 2026-08-07 | Does not meet — action A-17-03 | Per study / major change | E7 — e7_interaction.json | Richard Watson Stephen Amudha
NFR-Q01 | Accuracy | Citation precision | CR-2026-02 | 2026-03 | DoD FMR answers must be traceable | ≥ 0.98 (set in QO-01) | 2026-10-07 | 0.979 (n=36) | 2026-08-07 | At boundary | Per study / major change | E5 — e5_grounding.json | Richard Watson Stephen Amudha
NFR-Q02 | Accuracy | Citation recall | CR-2026-02 | 2026-03 | DoD FMR answers must be traceable | ≥ 0.80 | 2026-10-07 | 0.826 (n=43) | 2026-08-07 | Meets | Per study / major change | E5 | Richard Watson Stephen Amudha
NFR-Q03 | Accuracy | Fact support rate | CR-2026-02 | 2026-03 | Grounded answers | ≥ 0.80 | 2026-10-07 | 0.815 (75/92) | 2026-08-07 | Meets | Per study / major change | E5 | Richard Watson Stephen Amudha
NFR-Q04 | Accuracy | Abstention when the corpus cannot answer | CR-2026-02 | 2026-03 | Refuse when the corpus cannot answer | ≥ 0.80 | 2026-10-07 | 0.783 (n=23) | 2026-08-07 | Does not meet — action A-17-04 | Per study / major change | E5 | Richard Watson Stephen Amudha
NFR-Q05 | Accuracy | Golden regression suite (52 questions) | RV-2026-01 | 2026-07-29 | Golden suite created | ≥ 49/52 (baseline 2026-08-06) | 2026-10-07 | Blocked — corpus absent (9/52 by construction, 2026-09-22); run now aborts with the missing list | 2026-10-07 | Blocked — action A-17-05 | Every release | eval/run_eval.py; NC-2026-008 | Richard Watson Stephen Amudha
NFR-Q06 | Accuracy | Small talk answered without document citations | RV-2026-07 | 2026-10-06 | Acceptance testing | 100 % of acceptance probes | 2026-10-07 | Pass on v1.4.1 (after fix e0ed4d0) | 2026-10-06 | Meets | Every release; after every defect fix | TC-EM-RAG-103 run 4 | Richard Watson Stephen Amudha
NFR-S01 | Security | No cross-tenant leakage in answers | RV-2026-01 | 2026-08-07 | Isolation regression NC-2026-001 | 0 leaks | 2026-10-07 | 0 / 50 probes | 2026-08-07 | Meets | Per study / major change | E3 — e3_permission.json | Kishan Haravu Pradeep
NFR-S02 | Security | No out-of-namespace retrieval hits | RV-2026-01 | 2026-08-07 | Isolation regression NC-2026-001 | 0 hits | 2026-10-07 | 0 / 359 (all paths) after fix 4e27109 | 2026-08-07 | Meets | Per study / major change | e3b_path_isolation.json | Kishan Haravu Pradeep
NFR-S03 | Security | Prompt-injection success rate | SR-2026-01 | 2026-06-18 | Code audit: prompt injection | ≤ 5 % with defences | 2026-10-07 | 10.2 % undefended → 5.1 % with evidence envelope | 2026-08-07 | At boundary | Per study / major change | E4 — e4_injection.json; paper | Richard Watson Stephen Amudha
NFR-S04 | Security | Injection guards in every prompt path | SR-2026-01 | 2026-06-18 | Code audit: prompt injection | All paths | 2026-10-07 | 5 unit tests, run by CI on every push | 2026-10-07 | Meets | Every push and pull request | test_prompt_guards.py; CI | Richard Watson Stephen Amudha
NFR-S05 | Security | Public instance requires login | RV-2026-06 | 2026-10-06 | Public instance without login (NC-2026-009) | Unauthenticated API → 401, always | 2026-10-07 | 401 from GitHub's network every 6 h; was off 2026-07-30 → 10-06 (NC-2026-009) | 2026-10-07 | Meets since 2026-10-06 | Every release; after every defect fix | public-gate-check workflow run 37561803121 | Kishan Haravu Pradeep
NFR-S06 | Security | Logout ends the session | RV-2026-07 | 2026-10-06 | Acceptance testing | Replayed token → 401 | 2026-10-07 | 401 (fix e0ed4d0) | 2026-10-06 | Meets | Every release; after every defect fix | TC-EM-AUTH-101 AC-101.7 run 4 | Kishan Haravu Pradeep
NFR-S07 | Security | Only supported document types accepted | RV-2026-07 | 2026-10-06 | Acceptance testing | Binary/unsupported → 415 | 2026-10-07 | 415 (fix e0ed4d0) | 2026-10-06 | Meets | Every release; after every defect fix | TC-EM-DOC-102 DOC-102.5 run 4 | Kishan Haravu Pradeep
NFR-S08 | Security | Export gateway removes PII and keys | RV-2026-07 | 2026-10-06 | Acceptance testing | No sensitive value in redacted copy | 2026-10-07 | Pass incl. sk-/pk- keys (fix e0ed4d0) | 2026-10-06 | Meets | Every release; after every defect fix | TC-EM-EXP-108 run 4 | Kishan Haravu Pradeep
NFR-R01 | Reliability | Health checks that exercise the function | RV-2026-07 | 2026-10-06 | Health check stayed green while embeddings failed (NC-2026-016) | All long-running services | 2026-10-07 | 4 of 6 services; Ollama check now makes a real embedding (2026-10-07); frontend/cloudflared none | 2026-10-07 | Partial — action A-17-06 | Every 15–30 s | docker-compose.yml; NC-2026-016 | Richard Watson Stephen Amudha
NFR-R02 | Reliability | Automatic recovery from a fatal GPU fault | Platform | 2026-06-26 | GPU faults on the shared platform | Unattended recovery | 2026-10-07 | /health 503 + watchdog + restart policy | 2026-09-22 | Meets | Every 15–30 s | backend/app/main.py; docker-compose.yml | Richard Watson Stephen Amudha
NFR-R03 | Reliability | Bounded logs | QMS G-11 | 2026-09-21 | Unbounded logs | 50 MB × 5 per service | 2026-10-07 | Applied to all six containers | 2026-10-06 | Meets | Each release | docker inspect; REG-07 | Richard Watson Stephen Amudha
NFR-R04 | Reliability | Customer data recoverable | QMS G-03; 2025 lesson #18 | 2026-09-21 | No backup of customer data | Restore tested ≤ 6 months; nightly off-site copy | 2026-10-07 | Restore verified 2026-09-22; checksum verified 2026-10-06; off-site schedule not installed | 2026-10-06 | Partial — action A-17-07 | Each release | TC-EM-BKP-113 | Kishan Haravu Pradeep
NFR-R05 | Reliability | Reproducible builds | NC-2026-006 | 2026-09-04 | Build broke on a moving dependency | All dependencies pinned | 2026-10-07 | NeMo pinned (60ce9407); ollama/cloudflared images unpinned | 2026-09-22 | Partial | Each release | Dockerfiles; REG-02 | Richard Watson Stephen Amudha
NFR-M01 | Maintainability | Automated regression on every change | RV-2026-05 | 2026-09-28 | Failing tests unnoticed (NC-2026-010) | Every push | 2026-10-07 | CI: backend 50, voice 131, type-check; proven to fail on a broken test | 2026-10-07 | Meets | Every push and pull request | CI runs 37561379960 / 37561804619 | Richard Watson Stephen Amudha
NFR-M02 | Maintainability | Running instance traceable to source | QMS G-01 | 2026-09-21 | Instance not traceable to source | Version + commit reported | 2026-10-07 | 1.4.1 / f1b8445 on backend, voice and front end | 2026-10-06 | Meets | Every release; after every defect fix | /api/version; TC-EM-REL-106 | Richard Watson Stephen Amudha
NFR-D01 | Data protection | Customer data never leaves the perimeter | DR-2025-09 (2025 SOW) | 2025-08-05 | Fully offline, on-premises system | Absolute | 2026-10-07 | All inference local; no cloud AI path enabled | 2026-10-07 | Meets | Before and after any configuration change | docker-compose.yml; REG-02 | Kishan Haravu Pradeep
NFR-D02 | Data protection | Encryption at rest | QMS R-13 | 2026-09-21 | Encryption at rest | Decision required | 2026-10-07 | None (SQLite, uploads, indexes unencrypted) | 2026-09-21 | Gap — decision A-17-08 | Each release | REG-03 R-13 | Kishan Haravu Pradeep
NFR-D03 | Data protection | Retention bounded per data class | QMS R-06 | 2026-09-21 | Retention | Per class, in days (decision) | 2026-10-07 | No policy | 2026-09-21 | Gap — decision A-17-08 | Each release | REG-03 R-06 | Kishan Haravu Pradeep

## 2025 NFRs
2025 appliance — non-functional requirements
From the 2025 SOW, design inputs and the May–Sep 2025 lessons log (CR-2025-01…04).
NFR ID | Category | Requirement | Target | Result | Date | Source | Status | Carried into 2026
NFR-2025-01 | Data protection | Fully offline, on-premises operation | Absolute | Met — appliance delivered offline (Sep 2025) | 2025-09-20 | SOW 2025-08-05; ECH-QMS-010 | Met | Carried into NFR-D01
NFR-2025-02 | Performance | Hardware sized for offline RAG (RTX 4090 GPU) | Design input | Met | 2025-07-10 | ECH-QMS-011; prototype review DR-2025-05 | Met | Replaced by the DGX Spark (2026)
NFR-2025-03 | Performance | API responsive under load (LLM and transcription together) | No delays under load | Container limits rebalanced (CR-2025-01) | 2025 | 2025 lessons log #1 | Met | Carried into NFR-P01
NFR-2025-04 | Performance | No latency spikes on large audio | Streaming without spikes | Progressive streaming and async buffering (CR-2025-01) | 2025 | 2025 lessons log #9 | Met | Carried into NFR-P06
NFR-2025-05 | Security | No secrets in plain text | Tokens stored securely | JWT and environment vault (CR-2025-02) | 2025 | 2025 lessons log #3 | Met | Carried into NFR-S05/S06
NFR-2025-06 | Reliability | Back up before redeploying | Snapshot before every redeploy | Automated pre-redeploy snapshot (CR-2025-01) | 2025 | 2025 lessons log #18 | Met | Carried into NFR-R04
NFR-2025-07 | Maintainability | Versioned deployments | Every image tagged | Mandatory version tagging (CR-2025-01) | 2025 | 2025 lessons log #2 | Met | Carried into NFR-M02
NFR-2025-08 | Service | Post-delivery support | 1-year warranty; 20 h consulting | Defined in the SOW | 2025-08-05 | SOW; ECH-QMS-013 | Met (defined) | —
NFR-2025-09 | Records | Project records retained | 7 years | ECH-QMS-008 | 2025 | ECH-QMS-008 | Met | Carried into SOP-01

## Measurement history
Measurement history
Golden-suite runs are listed individually from eval/reports; other measurements from the paper harness, acceptance runs and CI.
Date | Version | NFR | Measurement | Result | Status / note | Evidence
2026-07-29 12:39 | v1.3.0 | NFR-Q05 | Golden suite | 29/52 | First run of the new harness | eval/reports/eval_20260729-123923.json
2026-07-29 12:48 | v1.3.0 | NFR-Q05 | Golden suite | 27/52 | Tuning run | eval/reports/eval_20260729-124803.json
2026-07-29 13:00 | v1.3.0 | NFR-Q05 | Golden suite | 44/52 | Tuning run | eval/reports/eval_20260729-130027.json
2026-07-29 13:09 | v1.3.0 | NFR-Q05 | Golden suite | 47/52 | Tuning run | eval/reports/eval_20260729-130900.json
2026-07-29 13:18 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-131815.json
2026-07-29 13:45 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-134521.json
2026-07-29 18:45 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-184535.json
2026-07-29 18:54 | v1.3.0 | NFR-Q05 | Golden suite | 47/52 | Tuning run | eval/reports/eval_20260729-185435.json
2026-07-29 19:51 | v1.3.0 | NFR-Q05 | Golden suite | 43/52 | Tuning run | eval/reports/eval_20260729-195109.json
2026-07-29 19:59 | v1.3.0 | NFR-Q05 | Golden suite | 0/7 | Smoke subset (7 questions) | eval/reports/eval_20260729-195914.json
2026-07-29 20:03 | v1.3.0 | NFR-Q05 | Golden suite | 0/7 | Smoke subset (7 questions) | eval/reports/eval_20260729-200328.json
2026-07-29 20:10 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-201050.json
2026-07-29 20:33 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-203340.json
2026-07-29 20:42 | v1.3.0 | NFR-Q05 | Golden suite | 49/52 | Tuning run | eval/reports/eval_20260729-204248.json
2026-07-29 21:52 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-215246.json
2026-07-29 22:47 | v1.3.0 | NFR-Q05 | Golden suite | 46/52 | Tuning run | eval/reports/eval_20260729-224713.json
2026-07-29 22:56 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-225633.json
2026-07-29 22:56 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-225644.json
2026-07-29 23:10 | v1.3.0 | NFR-Q05 | Golden suite | 48/52 | Tuning run | eval/reports/eval_20260729-231034.json
2026-07-30 01:59 | v1.3.0 | NFR-Q05 | Golden suite | 43/52 | Tuning run | eval/reports/eval_20260730-015940.json
2026-07-30 02:06 | v1.3.0 | NFR-Q05 | Golden suite | 50/52 | Baseline 50/52 — release gate set at ≥ 49 | eval/reports/eval_20260730-020659.json
2026-08-06 14:22 | v1.3.0 | NFR-Q05 | Golden suite | 42/52 | Regression detected: isolation bypass (NC-2026-001) | eval/reports/eval_20260806-142233.json
2026-08-06 14:32 | v1.3.0 | NFR-Q05 | Golden suite | 49/52 | After fix 4e27109 | eval/reports/eval_20260806-143249.json
2026-08-07 | v1.3.0 | NFR-P01 | Paper harness E1 | median 3.31 s; p95 15.17 s (n=30) | Meets | eval/paper/results/e1_latency.json
2026-08-07 | v1.3.0 | NFR-P02 / P03 | Paper harness E1 | Retrieval 2.8 % of latency; filter 0.08 ms | Meets | eval/paper/results
2026-08-07 | v1.3.0 | NFR-P04 | Paper harness E4 | First audible reply median 636 ms; p95 894 ms (n=10) vs 866 ms single loop | Meets | eval/paper/results
2026-08-07 | v1.3.0 | NFR-P07 | Paper harness E7 | Barge-in stop median 2.13 s; success 1.00 (n=8) | Does not meet | eval/paper/results
2026-08-07 | v1.3.0 | NFR-Q01…Q04 | Paper harness E2/E3/E5 | Citation precision 0.979; recall 0.826; fact support 0.815; abstention 0.783 | Partial | eval/paper/results/SUMMARY.json
2026-08-07 | v1.3.0 | NFR-S01 / S02 / S03 | Paper harness E6/E8 | 0/50 leaks; 0/359 out-of-namespace; injection 10.2 % → 5.1 % | Meets / at boundary | eval/paper/results
2026-09-21 | v1.4.0 | NFR-P05 / P06 | 12 spoken turns, 2 personas | First reply 0.14–0.49 s on GPU; final STT 70–130 ms | Meets | commit ff29843
2026-09-22 | v1.4.0 | NFR-R04 | Restore test | Restore into a throwaway volume: integrity_check ok, 32 tables | Meets | backup_checksum_20260922.sha256
2026-09-22 13:53 | v1.4.0 | NFR-Q05 | Golden suite | 9/52 | Corpus absent (NC-2026-008) — blocked | eval/reports/eval_20260922-135322.json
2026-10-06 | v1.4.1 | NFR-Q06, S06–S08, M02 | Acceptance suite run 1 | 4 failures (logout, upload type, small talk, export key formats) | Fail | 15_Testing/Execution_Records/run1
2026-10-06 | v1.4.1 | NFR-Q06, S06–S08, M02 | Acceptance suite run 4 (after fixes) | 11/11 executable cases pass | Pass | 15_Testing/Execution_Records/run4
2026-10-06 | v1.4.1 | NFR-R03 | Container configuration | Log rotation 50 MB × 5 on all six containers | Meets | docker inspect
2026-10-07 | v1.4.1 | NFR-M01, S04 | CI | Backend 50, voice 131 tests, type-check 0 errors; proven red on a broken test | Meets | GitHub Actions CI
2026-10-07 | v1.4.1 | NFR-S05 | External login check | Unauthenticated API → 401 from GitHub's network, every 6 h | Meets | public-gate-check workflow
2026-10-07 | v1.4.1 | NFR-R01 | Health checks | Ollama check makes a real embedding; 4 of 6 services checked | Partial | docker-compose.yml

## Monitoring plan
Monitoring plan
Monitor | NFRs covered | Frequency | Mechanism | In place
Unit and type checks | NFR-S04, NFR-M01 | Every push and pull request | GitHub Actions CI | Since 2026-10-07
Acceptance suite (13 test cases) | NFR-Q06, S05–S08, M02 | Every release; after every defect fix | run_tests.py — runs 1–4 on 2026-10-06 | Since 2026-10-06
Golden evaluation (52 questions) | NFR-Q05 | Every release | eval/run_eval.py (aborts if the corpus is missing) | Since 2026-07-29; blocked since 2026-09-15
Research harness E1–E10 | NFR-P01–P04, P07, Q01–Q04, S01–S03 | Per study / major change | eval/paper/ | 2026-08-07
External login gate check | NFR-S05 | Every 6 hours | public-gate-check workflow | Since 2026-10-07
Container health checks | NFR-R01, R02 | Every 15–30 s | docker-compose healthchecks | Continuous
Runtime-settings drift check | NFR-S05, D01 | Before and after any configuration change | scripts/check_runtime_config.sh | Since 2026-10-07
Register review | All | Each release and each management review | This document / REG-09 | From 2026-10-07

## Summary
Summary — live formulas
Category | NFRs | Meeting target | Not yet (action open)
Performance
Accuracy
Security
Reliability
Maintainability
Data protection
Total