## Finding 6 J-M
Finding | J — Corrective action | K — Root cause | L — Correction | M — Date
6 — OFI, clause 6.1.1 (SY / Alexander Peter) | Carry out and record an AI Impact Assessment for EchoMind covering intended use, affected people, data protection and consent for recordings, accuracy, bias, transparency, human oversight, security and misuse, model licensing, environmental impact and governance. Add an AI impact assessment step to the design and development procedure (SOP-05) for every new feature, use case, model and release. Add AI-specific risks to the risk register and review them at management review. Implement the actions from the assessment, starting with a recording notice and consent guidance for meeting participants. | SOP-05 required functional, non-functional, security and data-protection requirements but no consolidated AI impact assessment. Ethical and governance impacts were handled through individual controls (offline processing, export redaction, citations, tenant isolation, human release authorisation) without one documented, systematic evaluation. | AI Impact Assessment completed for EchoMind v1.4.1 and all current use cases (EM26-35, 20 Oct 2026): 15 impact areas, 13 use cases screened, 9 actions with owners. SOP-05 revised (revision 1.2, §7a) to require the assessment for every new feature, use case, model and release. AI risks R-15 to R-18 added to the risk register; finding logged as OFI-2026-06. | Assessment, SOP-05 revision and risk register: 20 Oct 2026, approval before 22 Oct 2026. Assessment actions: recording notice and consent guidance 30 Nov 2026; bias measurement 31 Jan 2027. Effectiveness checked at the internal audit, 9–13 Nov 2026.